## Event Info
Event Information
Event Number |  | 70308
Event Name |  | S3 VPN Big Pipe
Event Download File Name |  | C:\Users\waitenc\Downloads\70308-S3 VPN Big Pipe.xls
STP Number | STP Name |  | Implementation Context | Backout Context | Included in Extract | Imp Context treated as Backout Context | Process | Macro Version | Date Generated
[7 empty] | Event Reformat | v026.20230309 | 2023-04-04 12:58
[7 empty] | Shape of Event | v026.20230309 | 2023-04-04 12:58
Event Flow Diagram
Resource Profile
Cyclic Report
466045 | S3 VPN Big Pipe SoE |  | Y (108) | N (0) | Y | No
466046 | S3 VPN Big Pipe BO |  | Y (66) | N (0) | Y | Yes

## Shape of Event
[5 empty] | 2023-04-16 | [23 empty] | 2023-04-17 | [23 empty] | 2023-04-18 | [23 empty] | 2023-04-19 | [23 empty] | 2023-04-20
STP Num | Name | Context | Type | Status | 45032 | 45032.0417 | 45032.0833 | 45032.125 | 45032.1667 | 45032.2083 | 45032.25 | 45032.2917 | 45032.3333 | 45032.375 | 45032.4167 | 45032.4583 | 45032.5 | 45032.5417 | 45032.5833 | 45032.625 | 45032.6667 | 45032.7083 | 45032.75 | 45032.7917 | 45032.8333 | 45032.875 | 45032.9167 | 45032.9583 | 45033 | 45033.0417 | 45033.0833 | 45033.125 | 45033.1667 | 45033.2083 | 45033.25 | 45033.2917 | 45033.3333 | 45033.375 | 45033.4167 | 45033.4583 | 45033.5 | 45033.5417 | 45033.5833 | 45033.625 | 45033.6667 | 45033.7083 | 45033.75 | 45033.7917 | 45033.8333 | 45033.875 | 45033.9167 | 45033.9583 | 45034 | 45034.0417 | 45034.0833 | 45034.125 | 45034.1667 | 45034.2083 | 45034.25 | 45034.2917 | 45034.3333 | 45034.375 | 45034.4167 | 45034.4583 | 45034.5 | 45034.5417 | 45034.5833 | 45034.625 | 45034.6667 | 45034.7083 | 45034.75 | 45034.7917 | 45034.8333 | 45034.875 | 45034.9167 | 45034.9583 | 45035 | 45035.0417 | 45035.0833 | 45035.125 | 45035.1667 | 45035.2083 | 45035.25 | 45035.2917 | 45035.3333 | 45035.375 | 45035.4167 | 45035.4583 | 45035.5 | 45035.5417 | 45035.5833 | 45035.625 | 45035.6667 | 45035.7083 | 45035.75 | 45035.7917 | 45035.8333 | 45035.875 | 45035.9167 | 45035.9583 | 45036 | 45036.0417 | 45036.0833 | 45036.125 | 45036.1667 | 45036.2083 | 45036.25 | 45036.2917 | 45036.3333 | 45036.375 | 45036.4167 | 45036.4583 | 45036.5 | 45036.5417 | 45036.5833 | 45036.625 | 45036.6667 | 45036.7083 | 45036.75 | 45036.7917 | 45036.8333 | 45036.875 | 45036.9167 | 45036.9583
466045 |  | Imp | STP
466045 | S3 VPN Big Pipe SoE | Imp | STP | Pending
466045 |  | Imp | Stage
466045 | 2 : [ Implementation Readiness ] | Imp | Stage | Pending
466045 | 3 : [ Readiness Check ] | Imp | Stage | Pending
466045 | 4 : [ Milestone - Connectivity Confirmed ] | Imp | Stage | Pending
466045 | 5 : [ ON ICE AutoSys Jobs before changes - Sunday ] | Imp | Stage | Pending
466045 | 6 : [ cmd file Deployments - Monday 04:00 ] | Imp | Stage | Pending
466045 | 7 : [ Adhoc Job runs to prove Autosys Setup ] | Imp | Stage | Pending
466045 | 8 : [ OFF ICE AutoSys Jobs after changes - Return to BAU ] | Imp | Stage | Pending
466045 | 9 : [ Milestone - Deployments Complete ] | Imp | Stage | Pending
466045 | 10 : [ Monday Job Monitoring ] | Imp | Stage | Pending
466045 | 11 : [ cmd file Deployments - Monday 12.00 ] | Imp | Stage | Pending
466045 | 12 : [ cmd file Deployments - Monday 12.00 ] | Imp | Stage | Pending
466045 | 13 : [ Monitoring - Group 2 Monday ] | Imp | Stage | Pending
466045 | 14 : [ Monitoring - Group 2 Tuesday ] | Imp | Stage | Pending
466045 | 15 : [ cmd file Deployments - Tuesday 07:30 ] | Imp | Stage | Pending
466045 | 16 : [ Monitoring - Group 3 Tuesday ] | Imp | Stage | Pending
466045 | 17 : [ Monitoring - Group 3 Wednesday ] | Imp | Stage | Pending
466046 |  | Bo | STP
466046 | S3 VPN Big Pipe BO | Bo | STP | Pending
466046 |  | Bo | Stage
466046 | 1 : [ Prepare for Backout ] | Bo | Stage | Pending
466046 | 2 : [ Backout Dynamics cmd files Changes - First Group ] | Bo | Stage | Pending
466046 | 3 : [ Enhanced Job Monitoring - First Group ] | Bo | Stage | Pending
466046 | 4 : [ Backout Dynamics cmd files Changes - Second Group ] | Bo | Stage | Pending
466046 | 5 : [ Enhanced Job Monitoring - Second Group ] | Bo | Stage | Pending
466046 | 6 : [ Enhanced Job Monitoring - Second Group ] | Bo | Stage | Pending
466046 | 7 : [ Backout Dynamics cmd files Changes - Third Group ] | Bo | Stage | Pending
466046 | 8 : [ Enhanced Job Monitoring - Third Group ] | Bo | Stage | Pending
466046 | 9 : [ Enhanced Job Monitoring - Third Group ] | Bo | Stage | Pending
Note on B4: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Start Time: Sun 16/04/2023 08:30 End Time: Wed 19/04/2023 08:30 Status: Pending
Note on O4: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Start Time: Sun 16/04/2023 08:30 End Time: Wed 19/04/2023 08:30 Status: Pending
Note on B6: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 2 [ Implementation Readiness ] Start Time: Sun 16/04/2023 08:30 End Time: Sun 16/04/2023 08:40 Status: Pending
Note on O6: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 2 [ Implementation Readiness ] Start Time: Sun 16/04/2023 08:30 End Time: Sun 16/04/2023 08:40 Status: Pending
Note on B7: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 3 [ Readiness Check ] Start Time: Sun 16/04/2023 09:00 End Time: Sun 16/04/2023 09:05 Status: Pending
Note on P7: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 3 [ Readiness Check ] Start Time: Sun 16/04/2023 09:00 End Time: Sun 16/04/2023 09:05 Status: Pending
Note on B8: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 4 [ Milestone - Connectivity Confirmed ] Start Time: Sun 16/04/2023 09:05 End Time: Sun 16/04/2023 09:05 Status: Pending
Note on P8: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 4 [ Milestone - Connectivity Confirmed ] Start Time: Sun 16/04/2023 09:05 End Time: Sun 16/04/2023 09:05 Status: Pending
Note on B9: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 5 [ ON ICE AutoSys Jobs before changes - Sunday ] Start Time: Sun 16/04/2023 09:05 End Time: Sun 16/04/2023 09:15 Status: Pending
Note on P9: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 5 [ ON ICE AutoSys Jobs before changes - Sunday ] Start Time: Sun 16/04/2023 09:05 End Time: Sun 16/04/2023 09:15 Status: Pending
Note on B10: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 6 [ cmd file Deployments - Monday 04:00 ] Start Time: Mon 17/04/2023 04:00 End Time: Mon 17/04/2023 04:15 Status: Pending
Note on AI10: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 6 [ cmd file Deployments - Monday 04:00 ] Start Time: Mon 17/04/2023 04:00 End Time: Mon 17/04/2023 04:15 Status: Pending
Note on B11: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 7 [ Adhoc Job runs to prove Autosys Setup ] Start Time: Mon 17/04/2023 04:15 End Time: Mon 17/04/2023 05:00 Status: Pending
Note on AI11: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 7 [ Adhoc Job runs to prove Autosys Setup ] Start Time: Mon 17/04/2023 04:15 End Time: Mon 17/04/2023 05:00 Status: Pending
Note on B12: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 8 [ OFF ICE AutoSys Jobs after changes - Return to BAU ] Start Time: Mon 17/04/2023 05:00 End Time: Mon 17/04/2023 05:20 Status: Pending
Note on AJ12: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 8 [ OFF ICE AutoSys Jobs after changes - Return to BAU ] Start Time: Mon 17/04/2023 05:00 End Time: Mon 17/04/2023 05:20 Status: Pending
Note on B13: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 9 [ Milestone - Deployments Complete ] Start Time: Mon 17/04/2023 05:20 End Time: Mon 17/04/2023 05:20 Status: Pending
Note on AJ13: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 9 [ Milestone - Deployments Complete ] Start Time: Mon 17/04/2023 05:20 End Time: Mon 17/04/2023 05:20 Status: Pending
Note on B14: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 10 [ Monday Job Monitoring ] Start Time: Mon 17/04/2023 05:20 End Time: Mon 17/04/2023 11:20 Status: Pending
Note on AJ14: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 10 [ Monday Job Monitoring ] Start Time: Mon 17/04/2023 05:20 End Time: Mon 17/04/2023 11:20 Status: Pending
Note on B15: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 11 [ cmd file Deployments - Monday 12.00 ] Start Time: Mon 17/04/2023 12:00 End Time: Mon 17/04/2023 13:00 Status: Pending
Note on AQ15: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 11 [ cmd file Deployments - Monday 12.00 ] Start Time: Mon 17/04/2023 12:00 End Time: Mon 17/04/2023 13:00 Status: Pending
Note on B16: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 12 [ cmd file Deployments - Monday 12.00 ] Start Time: Mon 17/04/2023 12:00 End Time: Mon 17/04/2023 12:10 Status: Pending
Note on AQ16: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 12 [ cmd file Deployments - Monday 12.00 ] Start Time: Mon 17/04/2023 12:00 End Time: Mon 17/04/2023 12:10 Status: Pending
Note on B17: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 13 [ Monitoring - Group 2 Monday ] Start Time: Mon 17/04/2023 12:55 End Time: Mon 17/04/2023 20:55 Status: Pending
Note on AQ17: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 13 [ Monitoring - Group 2 Monday ] Start Time: Mon 17/04/2023 12:55 End Time: Mon 17/04/2023 20:55 Status: Pending
Note on B18: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 14 [ Monitoring - Group 2 Tuesday ] Start Time: Tue 18/04/2023 06:00 End Time: Tue 18/04/2023 10:00 Status: Pending
Note on BI18: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 14 [ Monitoring - Group 2 Tuesday ] Start Time: Tue 18/04/2023 06:00 End Time: Tue 18/04/2023 10:00 Status: Pending
Note on B19: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 15 [ cmd file Deployments - Tuesday 07:30 ] Start Time: Tue 18/04/2023 07:30 End Time: Tue 18/04/2023 07:40 Status: Pending
Note on BJ19: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 15 [ cmd file Deployments - Tuesday 07:30 ] Start Time: Tue 18/04/2023 07:30 End Time: Tue 18/04/2023 07:40 Status: Pending
Note on B20: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 16 [ Monitoring - Group 3 Tuesday ] Start Time: Tue 18/04/2023 09:05 End Time: Tue 18/04/2023 17:30 Status: Pending
Note on BL20: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 16 [ Monitoring - Group 3 Tuesday ] Start Time: Tue 18/04/2023 09:05 End Time: Tue 18/04/2023 17:30 Status: Pending
Note on B21: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 17 [ Monitoring - Group 3 Wednesday ] Start Time: Wed 19/04/2023 08:00 End Time: Wed 19/04/2023 08:30 Status: Pending
Note on CI21: STP: 466045 - S3 VPN Big Pipe SoE Context: Imp Stage No: 17 [ Monitoring - Group 3 Wednesday ] Start Time: Wed 19/04/2023 08:00 End Time: Wed 19/04/2023 08:30 Status: Pending
Note on B23: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Start Time: Mon 17/04/2023 11:30 End Time: Thu 20/04/2023 08:30 Status: Pending
Note on AP23: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Start Time: Mon 17/04/2023 11:30 End Time: Thu 20/04/2023 08:30 Status: Pending
Note on B25: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 1 [ Prepare for Backout ] Start Time: Mon 17/04/2023 11:30 End Time: Mon 17/04/2023 12:30 Status: Pending
Note on AP25: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 1 [ Prepare for Backout ] Start Time: Mon 17/04/2023 11:30 End Time: Mon 17/04/2023 12:30 Status: Pending
Note on B26: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 2 [ Backout Dynamics cmd files Changes - First Group ] Start Time: Mon 17/04/2023 12:00 End Time: Mon 17/04/2023 12:35 Status: Pending
Note on AQ26: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 2 [ Backout Dynamics cmd files Changes - First Group ] Start Time: Mon 17/04/2023 12:00 End Time: Mon 17/04/2023 12:35 Status: Pending
Note on B27: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 3 [ Enhanced Job Monitoring - First Group ] Start Time: Mon 17/04/2023 12:30 End Time: Mon 17/04/2023 16:30 Status: Pending
Note on AQ27: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 3 [ Enhanced Job Monitoring - First Group ] Start Time: Mon 17/04/2023 12:30 End Time: Mon 17/04/2023 16:30 Status: Pending
Note on B28: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 4 [ Backout Dynamics cmd files Changes - Second Group ] Start Time: Tue 18/04/2023 08:00 End Time: Tue 18/04/2023 08:35 Status: Pending
Note on BK28: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 4 [ Backout Dynamics cmd files Changes - Second Group ] Start Time: Tue 18/04/2023 08:00 End Time: Tue 18/04/2023 08:35 Status: Pending
Note on B29: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 5 [ Enhanced Job Monitoring - Second Group ] Start Time: Tue 18/04/2023 12:55 End Time: Tue 18/04/2023 20:55 Status: Pending
Note on BO29: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 5 [ Enhanced Job Monitoring - Second Group ] Start Time: Tue 18/04/2023 12:55 End Time: Tue 18/04/2023 20:55 Status: Pending
Note on B30: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 6 [ Enhanced Job Monitoring - Second Group ] Start Time: Wed 19/04/2023 06:00 End Time: Wed 19/04/2023 10:00 Status: Pending
Note on CG30: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 6 [ Enhanced Job Monitoring - Second Group ] Start Time: Wed 19/04/2023 06:00 End Time: Wed 19/04/2023 10:00 Status: Pending
Note on B31: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 7 [ Backout Dynamics cmd files Changes - Third Group ] Start Time: Wed 19/04/2023 08:00 End Time: Wed 19/04/2023 08:35 Status: Pending
Note on CI31: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 7 [ Backout Dynamics cmd files Changes - Third Group ] Start Time: Wed 19/04/2023 08:00 End Time: Wed 19/04/2023 08:35 Status: Pending
Note on B32: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 8 [ Enhanced Job Monitoring - Third Group ] Start Time: Wed 19/04/2023 09:05 End Time: Wed 19/04/2023 17:30 Status: Pending
Note on CJ32: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 8 [ Enhanced Job Monitoring - Third Group ] Start Time: Wed 19/04/2023 09:05 End Time: Wed 19/04/2023 17:30 Status: Pending
Note on B33: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 9 [ Enhanced Job Monitoring - Third Group ] Start Time: Thu 20/04/2023 08:00 End Time: Thu 20/04/2023 08:30 Status: Pending
Note on DG33: STP: 466046 - S3 VPN Big Pipe BO Context: Bo Stage No: 9 [ Enhanced Job Monitoring - Third Group ] Start Time: Thu 20/04/2023 08:00 End Time: Thu 20/04/2023 08:30 Status: Pending

## All Imp (hidden)
ID | Task Type | Phase | ID | Predecessors | Successors | Duration | Start Time | End Time | Explicit Start Time | Title | Owner | Team | Description | Technical Detail | Notes | SoE Name | SoE Number | Skipped | User Def 1 | User Def 2 | User Def 3 | User Def 4 | State | Evt ID | Event Crit Path | ID | Predecessors | Successors | User Def 5 | User Def 6
1.0:(S3 VPN Big Pipe SoE) | Stage | Pre | 1.0 | None | None | 1h 00m | 14-04-23 09:00 | 14-04-23 10:00 | - | Pre-Implementation Access and Backup Activities | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 1 | N | 1.0:(466045) | None | None
1.1:(S3 VPN Big Pipe SoE) | Task | Pre | 1.1 | None | None | 1h 00m | 14-04-23 09:00 | 14-04-23 10:00 | 14-04-23 09:00 | Confirm Dynamics Team access has been requested and granted |  | D365 |  |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 2 | N | 1.1:(466045) | None | None
1.2:(S3 VPN Big Pipe SoE) | Task | Pre | 1.2 | None | None | 1h 00m | 14-04-23 09:00 | 14-04-23 10:00 | 14-04-23 09:00 | Confirm D365 Autosys ReadOnly access requested |  | Implementation Manager | Confirm D365 Autosys ReadOnly access requested for Implementation Manager |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 3 | N | 1.2:(466045) | None | None
1.3:(S3 VPN Big Pipe SoE) | Task | Pre | 1.3 | None | None | 1h 00m | 14-04-23 09:00 | 14-04-23 10:00 | 14-04-23 09:00 | Confirm EE Team have requested all the required accesses |  | EE Team | Confirm EE Team have requested all the required accesses Autosys access etc Ensure access is granted for Service Account Service-Crmwdlprdapi to allow deployment of the Solution |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 4 | N | 1.3:(466045) | None | None
1.4:(S3 VPN Big Pipe SoE) | Task | Pre | 1.4 | None | None | 1h 00m | 14-04-23 09:00 | 14-04-23 10:00 | 14-04-23 09:00 | EE Team to check Production Servers have sufficient space |  | EE Team | EE Team to check Production Servers have sufficient space If there are any any issues with space on the Production server raise appropriate tickets to tidy up |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 5 | N | 1.4:(466045) | None | None
1.5:(S3 VPN Big Pipe SoE) | Task | Pre | 1.5 | None | None | 1h 00m | 14-04-23 09:00 | 14-04-23 10:00 | 14-04-23 09:00 | Confirm all Firewall changes are complete |  | Implementation Manager |  |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 6 | N | 1.5:(466045) | None | None
1.6:(S3 VPN Big Pipe SoE) | Checkpoint | Pre | 1.6 | None | None | 0h 00m | 14-04-23 10:00 | 14-04-23 10:00 | - | Pre-Implementation Access and Backup Activities | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 7 | N | 1.6:(466045) | None | None
2.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 2.0 | None | None | 0h 10m | 16-04-23 08:30 | 16-04-23 08:40 | - | Implementation Readiness |  |  |  | Shape:Exclude=Y |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 8 | N | 2.0:(466045) | None | None
2.1:(S3 VPN Big Pipe SoE) | Task | Imp | 2.1 | None | FS-2.3:(S3 VPN Big Pipe SoE), FS-2.4:(S3 VPN Big Pipe SoE), FS-2.2:(S3 VPN Big Pipe SoE) | 0h 00m | 16-04-23 08:30 | 16-04-23 08:30 | 16-04-23 08:30 | Start Implementation Time - 04:00 Friday |  | Implementation Manager |  |  |  | S3 VPN Big Pipe SoE | 466045 | Y |  |  |  |  | Review | 9 | N | 2.1:(466045) | None | FS-2.3:(466045), FS-2.4:(466045), FS-2.2:(466045)
2.2:(S3 VPN Big Pipe SoE) | Task | Imp | 2.2 | FS-2.1:(S3 VPN Big Pipe SoE) | None | 0h 10m | 16-04-23 08:30 | 16-04-23 08:40 | - | Open Command and Control Line and Teams Group Chat |  | Implementation Manager | Zoom - 7887 505 808 Open Teams Group Chat for implementation and invite all resources |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 10 | N | 2.2:(466045) | FS-2.1:(466045) | None
2.3:(S3 VPN Big Pipe SoE) | Task | Imp | 2.3 | FS-2.1:(S3 VPN Big Pipe SoE) | None | 0h 10m | 16-04-23 08:30 | 16-04-23 08:40 | - | Inform System Operations that the implementation is about to Start |  | Implementation Manager | Inform System Operations that the implementation is about to start CONFIRMING THERE ARE NO KNOWN ISSUES which would prevent this implementation from starting. Send mail to ~ System Operations Offhost <fpitopm@natwest.com> ~ System Operations Mainframe <system.operations@rbs.co.uk> Sys Ops Off-Host: +44 131 626 6540 Sys Ops Mainframe : +44 131 626 6510 Also check the P1 / P2 Incident Dashboard | https://rbos.service-now.com/now/nav/ui/classic/params/target/%24pa_dashboard.do%3Fsysparm_dashboard%3D770beb991bec5550adf5a8e6b04bcb4b |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 11 | N | 2.3:(466045) | FS-2.1:(466045) | None
2.4:(S3 VPN Big Pipe SoE) | Task | Imp | 2.4 | FS-2.1:(S3 VPN Big Pipe SoE) | None | 0h 10m | 16-04-23 08:30 | 16-04-23 08:40 | - | Check MCR MCR1292210 is set to SCHEDULED |  | Implementation Manager |  |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 12 | N | 2.4:(466045) | FS-2.1:(466045) | None
2.5:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 2.5 | None | FS-3.1:(S3 VPN Big Pipe SoE) | 0h 00m | 16-04-23 08:40 | 16-04-23 08:40 | - | Implementation Readiness | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 13 | N | 2.5:(466045) | None | FS-3.1:(466045)
3.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 3.0 | None | None | 0h 05m | 16-04-23 09:00 | 16-04-23 09:05 | - | Readiness Check |  |  |  | Shape:Name=S3 VPN Connectivity Check Shape:Colour=205,225,243 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 14 | N | 3.0:(466045) | None | None
3.1:(S3 VPN Big Pipe SoE) | Task | Imp | 3.1 | FS-2.5:(S3 VPN Big Pipe SoE) | None | 0h 05m | 16-04-23 09:00 | 16-04-23 09:05 | 16-04-23 09:00 | Perform Curl to confirm connections are in place |  |  | Perform Curl to confirm connections are in place |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 15 | N | 3.1:(466045) | FS-2.5:(466045) | None
3.2:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 3.2 | None | FS-4.1:(S3 VPN Big Pipe SoE) | 0h 00m | 16-04-23 09:05 | 16-04-23 09:05 | - | Readiness Check | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 16 | N | 3.2:(466045) | None | FS-4.1:(466045)
4.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 4.0 | None | None | 0h 00m | 16-04-23 09:05 | 16-04-23 09:05 | - | Milestone - Connectivity Confirmed |  |  |  | Shape:Exclude=Y |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 17 | N | 4.0:(466045) | None | None
4.1:(S3 VPN Big Pipe SoE) | Task | Imp | 4.1 | FS-3.2:(S3 VPN Big Pipe SoE) | None | 0h 00m | 16-04-23 09:05 | 16-04-23 09:05 | - | Internal Checkpoint - Connectivity Confirmed - Start Changes |  | Implementation Manager |  | Shape:Exclude=Y |  | S3 VPN Big Pipe SoE | 466045 | Y |  |  |  |  | Review | 18 | N | 4.1:(466045) | FS-3.2:(466045) | None
4.2:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 4.2 | None | FS-5.1:(S3 VPN Big Pipe SoE) | 0h 00m | 16-04-23 09:05 | 16-04-23 09:05 | - | Milestone - Connectivity Confirmed | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 19 | N | 4.2:(466045) | None | FS-5.1:(466045)
5.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 5.0 | None | None | 0h 10m | 16-04-23 09:05 | 16-04-23 09:15 | - | ON ICE AutoSys Jobs before changes - Sunday |  |  |  | Shape:Name=ON ICE Jobs - First Group Shape:Colour=205,225,243 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 20 | N | 5.0:(466045) | None | None
5.1:(S3 VPN Big Pipe SoE) | Task | Imp | 5.1 | FS-4.2:(S3 VPN Big Pipe SoE) | FS-5.2:(S3 VPN Big Pipe SoE) | 0h 05m | 16-04-23 09:05 | 16-04-23 09:10 | - | EE Team - ON ICE Jobs |  | EE and D365 | EE Team - ON ICE Jobs Place following boxes ON ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Place following jobs ON ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 21 | N | 5.1:(466045) | FS-4.2:(466045) | FS-5.2:(466045)
5.2:(S3 VPN Big Pipe SoE) | Task | Imp | 5.2 | FS-5.1:(S3 VPN Big Pipe SoE) | None | 0h 05m | 16-04-23 09:10 | 16-04-23 09:15 | - | EE Team - Verfiy Jobs have been placed ON ICE |  | EE and D365 | EE Team - Verfiy Jobs have been placed ON ICE Confirm following boxes ON ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Confirm following jobs ON ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 22 | N | 5.2:(466045) | FS-5.1:(466045) | None
5.3:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 5.3 | None | FS-6.1:(S3 VPN Big Pipe SoE) | 0h 00m | 16-04-23 09:15 | 16-04-23 09:15 | - | ON ICE AutoSys Jobs before changes - Sunday | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 23 | N | 5.3:(466045) | None | FS-6.1:(466045)
6.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 6.0 | None | None | 0h 15m | 17-04-23 04:00 | 17-04-23 04:15 | - | cmd file Deployments - Monday 04:00 |  |  |  | Shape:Group=Group 1 Shape:Name= Deploy cmd Files - First Group Shape:Colour=205,225,243 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 24 | N | 6.0:(466045) | None | None
6.1:(S3 VPN Big Pipe SoE) | Task | Imp | 6.1 | FS-5.3:(S3 VPN Big Pipe SoE) | FS-6.2:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:00 | 17-04-23 04:05 | 17-04-23 04:00 | Dynamics - Create Backout Restore point - Dynamics SSIS Packages and cmd file Copy |  | EE and D365 | Dynamics - Create Backout Restore point - Dynamics SSIS Packages and cmd file Copy In production server backup all files in folders: /SSISPackages/Command /SSISPackages/DTX Specifically take backups of the following SSIS Package files: IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 25 | N | 6.1:(466045) | FS-5.3:(466045) | FS-6.2:(466045)
6.2:(S3 VPN Big Pipe SoE) | Task | Imp | 6.2 | FS-6.1:(S3 VPN Big Pipe SoE) | FS-6.3:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:05 | 17-04-23 04:10 | - | Dynamics - Copy SSIS Packages and cmd files to Production |  | EE and D365 | Dynamics - Copy SSIS Packages and cmd files to Production in folder /SSISPackages/Command IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd in folder /SSISPackages/DTX IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 26 | N | 6.2:(466045) | FS-6.1:(466045) | FS-6.3:(466045)
6.3:(S3 VPN Big Pipe SoE) | Task | Imp | 6.3 | FS-6.2:(S3 VPN Big Pipe SoE) | None | 0h 05m | 17-04-23 04:10 | 17-04-23 04:15 | - | Dynamics - Confirm SSIS Package and cmd file changes Successfully Deployed |  | EE and D365 | Dynamics - Confirm SSIS Package and cmd file changes Successfully Deployed Confirm in folder /SSISPackages/Command IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd Confirm in folder /SSISPackages/DTX IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 27 | N | 6.3:(466045) | FS-6.2:(466045) | None
6.4:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 6.4 | None | FS-7.1:(S3 VPN Big Pipe SoE) | 0h 00m | 17-04-23 04:15 | 17-04-23 04:15 | - | cmd file Deployments - Monday 04:00 | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 28 | N | 6.4:(466045) | None | FS-7.1:(466045)
7.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 7.0 | None | None | 0h 45m | 17-04-23 04:15 | 17-04-23 05:00 | - | Adhoc Job runs to prove Autosys Setup |  |  |  | Shape:Group=Group 1 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 29 | N | 7.0:(466045) | None | None
7.1:(S3 VPN Big Pipe SoE) | Task | Imp | 7.1 | FS-6.4:(S3 VPN Big Pipe SoE) | FS-7.2:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:15 | 17-04-23 04:20 | - | Dynamics - Force Start msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 |  | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 30 | N | 7.1:(466045) | FS-6.4:(466045) | FS-7.2:(466045)
7.2:(S3 VPN Big Pipe SoE) | Task | Imp | 7.2 | FS-7.1:(S3 VPN Big Pipe SoE) | FS-7.3:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:20 | 17-04-23 04:25 | - | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 31 | N | 7.2:(466045) | FS-7.1:(466045) | FS-7.3:(466045)
7.3:(S3 VPN Big Pipe SoE) | Task | Imp | 7.3 | FS-7.2:(S3 VPN Big Pipe SoE) | FS-7.4:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:25 | 17-04-23 04:30 | - | Dynamics - Force Start msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 32 | N | 7.3:(466045) | FS-7.2:(466045) | FS-7.4:(466045)
7.4:(S3 VPN Big Pipe SoE) | Task | Imp | 7.4 | FS-7.3:(S3 VPN Big Pipe SoE) | FS-7.5:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:30 | 17-04-23 04:35 | - | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 33 | N | 7.4:(466045) | FS-7.3:(466045) | FS-7.5:(466045)
7.5:(S3 VPN Big Pipe SoE) | Task | Imp | 7.5 | FS-7.4:(S3 VPN Big Pipe SoE) | FS-7.6:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:35 | 17-04-23 04:40 | - | Dynamics - Force Start msd.edi.prd.wdl.spinotebox.ep1 |  | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.spinotebox.ep1 On completion of msd.edi.prd.wdl.integrationinstructionspinote.ep1 the job msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 should run Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 34 | N | 7.5:(466045) | FS-7.4:(466045) | FS-7.6:(466045)
7.6:(S3 VPN Big Pipe SoE) | Task | Imp | 7.6 | FS-7.5:(S3 VPN Big Pipe SoE) | FS-7.7:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:40 | 17-04-23 04:45 | - | Dynamics Technical Check - Confirm both SPI Note jobs run as expected |  | EE and D365 | Dynamics Technical Check - Confirm both SPI Note jobs run as expected msd.edi.prd.wdl.integrationinstructionspinote.ep1 msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 35 | N | 7.6:(466045) | FS-7.5:(466045) | FS-7.7:(466045)
7.7:(S3 VPN Big Pipe SoE) | Task | Imp | 7.7 | FS-7.6:(S3 VPN Big Pipe SoE) | FS-7.8:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:45 | 17-04-23 04:50 | - | Dynamics - Force Start msd.edi.prd.wdl.cohorttranchebox.ep1 |  | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.cohorttranchebox.ep1 On completion of msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 the job msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 should run Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 36 | N | 7.7:(466045) | FS-7.6:(466045) | FS-7.8:(466045)
7.8:(S3 VPN Big Pipe SoE) | Task | Imp | 7.8 | FS-7.7:(S3 VPN Big Pipe SoE) | FS-7.9:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:50 | 17-04-23 04:55 | - | Dynamics Technical Check - Confirm both Cohort Tranche jobs run as expected |  | EE and D365 | Dynamics Technical Check - Confirm both Cohort Tranche jobs run as expected msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 37 | N | 7.8:(466045) | FS-7.7:(466045) | FS-7.9:(466045)
7.9:(S3 VPN Big Pipe SoE) | Task | Imp | 7.9 | FS-7.8:(S3 VPN Big Pipe SoE) | None | 0h 05m | 17-04-23 04:55 | 17-04-23 05:00 | - | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during job checkout |  | EE and D365 | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during job checkout Confirm data received on DataHub for the following jobs runs: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 msd.edi.prd.wdl.integrationinstructionspinote.ep1 msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 These jobs run hourly Monday to Friday, continue monitoring until we are happy data is being received. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 38 | N | 7.9:(466045) | FS-7.8:(466045) | None
7.10:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 7.10 | None | FS-8.1:(S3 VPN Big Pipe SoE) | 0h 00m | 17-04-23 05:00 | 17-04-23 05:00 | - | Adhoc Job runs to prove Autosys Setup | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 39 | N | 7.10:(466045) | None | FS-8.1:(466045)
8.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 8.0 | None | None | 0h 20m | 17-04-23 05:00 | 17-04-23 05:20 | - | OFF ICE AutoSys Jobs after changes - Return to BAU |  |  |  | Shape:Group=Group 1 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 40 | N | 8.0:(466045) | None | None
8.1:(S3 VPN Big Pipe SoE) | Task | Imp | 8.1 | FS-7.10:(S3 VPN Big Pipe SoE) | FS-8.2:(S3 VPN Big Pipe SoE) | 0h 10m | 17-04-23 05:00 | 17-04-23 05:10 | - | EE Team - OFF ICE Jobs |  | EE and D365 | EE Team - OFF ICE Jobs Place following boxes OFF ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Place following jobs OFF ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 41 | N | 8.1:(466045) | FS-7.10:(466045) | FS-8.2:(466045)
8.2:(S3 VPN Big Pipe SoE) | Task | Imp | 8.2 | FS-8.1:(S3 VPN Big Pipe SoE) | None | 0h 10m | 17-04-23 05:10 | 17-04-23 05:20 | - | EE Team - Verfiy Jobs have been placed OFF ICE |  | EE and D365 | EE Team - Verfiy Jobs have been placed OFF ICE Confirm following boxes OFF ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Confirm following jobs OFF ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 42 | N | 8.2:(466045) | FS-8.1:(466045) | None
8.3:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 8.3 | None | FS-9.1:(S3 VPN Big Pipe SoE) | 0h 00m | 17-04-23 05:20 | 17-04-23 05:20 | - | OFF ICE AutoSys Jobs after changes - Return to BAU | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 43 | N | 8.3:(466045) | None | FS-9.1:(466045)
9.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 9.0 | None | None | 0h 00m | 17-04-23 05:20 | 17-04-23 05:20 | - | Milestone - Deployments Complete |  |  |  | Shape:Name=Milestone - Group 1 Deployments Complete Shape:Exclude=Y |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 44 | N | 9.0:(466045) | None | None
9.1:(S3 VPN Big Pipe SoE) | Task | Imp | 9.1 | FS-8.3:(S3 VPN Big Pipe SoE) | None | 0h 00m | 17-04-23 05:20 | 17-04-23 05:20 | - | Internal Checkpoint - All Code Deployments Complete |  | Implementation Manager |  | Shape:Exclude=Y |  | S3 VPN Big Pipe SoE | 466045 | Y |  |  |  |  | Review | 45 | N | 9.1:(466045) | FS-8.3:(466045) | None
9.2:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 9.2 | None | FS-10.5:(S3 VPN Big Pipe SoE), FS-10.1:(S3 VPN Big Pipe SoE), FS-10.2:(S3 VPN Big Pipe SoE), FS-10.3:(S3 VPN Big Pipe SoE), FS-10.4:(S3 VPN Big Pipe SoE), FS-10.6:(S3 VPN Big Pipe SoE), FS-10.7:(S3 VPN Big Pipe SoE) | 0h 00m | 17-04-23 05:20 | 17-04-23 05:20 | - | Milestone - Deployments Complete | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 46 | N | 9.2:(466045) | None | FS-10.5:(466045), FS-10.1:(466045), FS-10.2:(466045), FS-10.3:(466045), FS-10.4:(466045), FS-10.6:(466045), FS-10.7:(466045)
10.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 10.0 | None | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | Monday Job Monitoring |  |  |  | Shape:Name=Enhanced Job Monitoring - First Group Shape:Colour=205,225,243 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 47 | N | 10.0:(466045) | None | None
10.1:(S3 VPN Big Pipe SoE) | Task | Imp | 10.1 | FS-9.2:(S3 VPN Big Pipe SoE) | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 48 | N | 10.1:(466045) | FS-9.2:(466045) | None
10.2:(S3 VPN Big Pipe SoE) | Task | Imp | 10.2 | FS-9.2:(S3 VPN Big Pipe SoE) | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 CUSTRM-72540 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 49 | N | 10.2:(466045) | FS-9.2:(466045) | None
10.3:(S3 VPN Big Pipe SoE) | Task | Imp | 10.3 | FS-9.2:(S3 VPN Big Pipe SoE) | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Job runs Daily - MTWTF - Hourly on xx:25 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 50 | N | 10.3:(466045) | FS-9.2:(466045) | None
10.4:(S3 VPN Big Pipe SoE) | Task | Imp | 10.4 | FS-9.2:(S3 VPN Big Pipe SoE) | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Job runs Daily - MTWTF - Hourly on xx:40 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 51 | N | 10.4:(466045) | FS-9.2:(466045) | None
10.5:(S3 VPN Big Pipe SoE) | Task | Imp | 10.5 | FS-9.2:(S3 VPN Big Pipe SoE) | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 52 | N | 10.5:(466045) | FS-9.2:(466045) | None
10.6:(S3 VPN Big Pipe SoE) | Task | Imp | 10.6 | FS-9.2:(S3 VPN Big Pipe SoE) | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.integrationinstructionspinote.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 53 | N | 10.6:(466045) | FS-9.2:(466045) | None
10.7:(S3 VPN Big Pipe SoE) | Task | Imp | 10.7 | FS-9.2:(S3 VPN Big Pipe SoE) | None | 6h 00m | 17-04-23 05:20 | 17-04-23 11:20 | - | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during Monitoring |  | DataHub | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during Monitoring Confirm data received on DataHub for the following jobs runs: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 msd.edi.prd.wdl.integrationinstructionspinote.ep1 msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 These jobs run hourly Monday to Friday, continue monitoring until we are happy data is being received. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 54 | N | 10.7:(466045) | FS-9.2:(466045) | None
10.8:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 10.8 | None | None | 0h 00m | 17-04-23 11:20 | 17-04-23 11:20 | - | Monday Job Monitoring | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 55 | N | 10.8:(466045) | None | None
11.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 11.0 | None | None | 1h 00m | 17-04-23 12:00 | 17-04-23 13:00 | - | cmd file Deployments - Monday 12.00 |  |  |  | Shape:Group=Group2 Shape:Name=Deploy cmd Files - Second Group |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 56 | N | 11.0:(466045) | None | None
11.1:(S3 VPN Big Pipe SoE) | Task | Imp | 11.1 | None | FS-11.2:(S3 VPN Big Pipe SoE) | 0h 10m | 17-04-23 12:00 | 17-04-23 12:10 | 17-04-23 12:00 | EE Team - Confirm msd.edi.prd.wdl.tranchesd365todh.ep1 not running |  | EE and D365 | EE Team - Confirm msd.edi.prd.wdl.tranchesd365todh.ep1 not running Job runs hourly at 55 minutes passed the hour. Ensure that the 11:55 job has completed and is not running before continuing. If there are issues with the job or it is running longer than expected this can be delayed until it is appropriate to perform the changes |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 57 | N | 11.1:(466045) | None | FS-11.2:(466045)
11.2:(S3 VPN Big Pipe SoE) | Task | Imp | 11.2 | FS-11.1:(S3 VPN Big Pipe SoE) | FS-11.3:(S3 VPN Big Pipe SoE) | 0h 10m | 17-04-23 12:10 | 17-04-23 12:20 | - | EE Team - ON ICE Jobs |  | EE and D365 | EE Team - ON ICE Jobs msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 58 | N | 11.2:(466045) | FS-11.1:(466045) | FS-11.3:(466045)
11.3:(S3 VPN Big Pipe SoE) | Task | Imp | 11.3 | FS-11.2:(S3 VPN Big Pipe SoE) | FS-11.4:(S3 VPN Big Pipe SoE) | 0h 10m | 17-04-23 12:20 | 17-04-23 12:30 | - | EE Team - Verfiy Jobs have been placed ON ICE |  | EE and D365 | EE Team - Verify Jobs have been placed ON ICE Confirm following job is ON ICE: msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 59 | N | 11.3:(466045) | FS-11.2:(466045) | FS-11.4:(466045)
11.4:(S3 VPN Big Pipe SoE) | Task | Imp | 11.4 | FS-11.3:(S3 VPN Big Pipe SoE) | FS-11.5:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 12:30 | 17-04-23 12:35 | - | Dynamics - Copy cmd files to Production |  | EE and D365 | Dynamics - Copy cmd files to Production in folder /SSISPackages/Command Tranches_D365_to_DH.cmd |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 60 | N | 11.4:(466045) | FS-11.3:(466045) | FS-11.5:(466045)
11.5:(S3 VPN Big Pipe SoE) | Task | Imp | 11.5 | FS-11.4:(S3 VPN Big Pipe SoE) | FS-11.6:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 12:35 | 17-04-23 12:40 | - | Dynamics - Confirm cmd file changes Successfully Deployed |  | EE and D365 | Dynamics - Confirm cmd file changes Successfully Deployed in folder /SSISPackages/Command Tranches_D365_to_DH.cmd Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 61 | N | 11.5:(466045) | FS-11.4:(466045) | FS-11.6:(466045)
11.6:(S3 VPN Big Pipe SoE) | Task | Imp | 11.6 | FS-11.5:(S3 VPN Big Pipe SoE) | FS-11.7:(S3 VPN Big Pipe SoE) | 0h 10m | 17-04-23 12:40 | 17-04-23 12:50 | - | EE Team - OFF ICE Jobs |  | EE and D365 | EE Team - OFF ICE Jobs msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 62 | N | 11.6:(466045) | FS-11.5:(466045) | FS-11.7:(466045)
11.7:(S3 VPN Big Pipe SoE) | Task | Imp | 11.7 | FS-11.6:(S3 VPN Big Pipe SoE) | None | 0h 10m | 17-04-23 12:50 | 17-04-23 13:00 | - | EE Team - Verfiy Jobs have been placed OFF ICE |  | EE and D365 | EE Team - Verfiy Jobs have been placed OFF ICE Confirm following job is OFF ICE: msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 63 | N | 11.7:(466045) | FS-11.6:(466045) | None
11.8:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 11.8 | None | None | 0h 00m | 17-04-23 13:00 | 17-04-23 13:00 | - | cmd file Deployments - Monday 12.00 | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 64 | N | 11.8:(466045) | None | None
12.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 12.0 | None | None | 0h 10m | 17-04-23 12:00 | 17-04-23 12:10 | - | cmd file Deployments - Monday 12.00 |  |  |  | Shape:Group=Group2 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 65 | N | 12.0:(466045) | None | None
12.1:(S3 VPN Big Pipe SoE) | Task | Imp | 12.1 | None | FS-12.2:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 12:00 | 17-04-23 12:05 | 17-04-23 12:00 | Dynamics - Copy cmd files to Production |  | EE and D365 | Dynamics - Copy cmd files to Production in folder /SSISPackages/Command IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd If any of the jobs are experiencing issues or running longer than expected, delay the change for the job until appropriate. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 66 | N | 12.1:(466045) | None | FS-12.2:(466045)
12.2:(S3 VPN Big Pipe SoE) | Task | Imp | 12.2 | FS-12.1:(S3 VPN Big Pipe SoE) | None | 0h 05m | 17-04-23 12:05 | 17-04-23 12:10 | - | Dynamics - Confirm cmd file changes Successfully Deployed |  | EE and D365 | Dynamics - Confirm cmd file changes Successfully Deployed in folder /SSISPackages/Command IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 67 | N | 12.2:(466045) | FS-12.1:(466045) | None
12.3:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 12.3 | None | None | 0h 00m | 17-04-23 12:10 | 17-04-23 12:10 | - | cmd file Deployments - Monday 12.00 | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 68 | N | 12.3:(466045) | None | None
13.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 13.0 | None | None | 8h 00m | 17-04-23 12:55 | 17-04-23 20:55 | - | Monitoring - Group 2 Monday |  |  |  | Shape:Name=Enhanced Job Monitoring - Second Group |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 69 | N | 13.0:(466045) | None | None
13.1:(S3 VPN Big Pipe SoE) | Task | Imp | 13.1 | None | None | 8h 00m | 17-04-23 12:55 | 17-04-23 20:55 | 17-04-23 12:55 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 This is to confirm that Tranches_D365_to_DH.cmd has been updated correctly. This jobs runs hourly on 15 mins passed the hour. Keep monitoring this job until is is confirmed that job has processed data. This is a possibility that the job may not get any data to process on Monday, if this is the case continue monitoring on Tuesday as required. If we are struggling to confirm the job check with Dynamics and the Event Manager when to stop monitoring. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 70 | N | 13.1:(466045) | None | None
13.2:(S3 VPN Big Pipe SoE) | Task | Imp | 13.2 | None | None | 0h 30m | 17-04-23 14:00 | 17-04-23 14:30 | 17-04-23 14:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 This is to confirm that IntegrationInstructionsR3_CoreCharges.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 71 | N | 13.2:(466045) | None | None
13.3:(S3 VPN Big Pipe SoE) | Task | Imp | 13.3 | None | None | 0h 30m | 17-04-23 17:00 | 17-04-23 17:30 | 17-04-23 17:00 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 This is to confirm that SwitcherBOT_Commercial_D365_to_DH.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 72 | N | 13.3:(466045) | None | None
13.4:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 13.4 | None | None | 0h 00m | 17-04-23 20:55 | 17-04-23 20:55 | - | Monitoring - Group 2 Monday | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 73 | N | 13.4:(466045) | None | None
14.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 14.0 | None | None | 4h 00m | 18-04-23 06:00 | 18-04-23 10:00 | - | Monitoring - Group 2 Tuesday |  |  |  | Shape:Name=Enhanced Job Monitoring - Second Group |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 74 | N | 14.0:(466045) | None | None
14.1:(S3 VPN Big Pipe SoE) | Task | Imp | 14.1 | None | None | 0h 30m | 18-04-23 06:00 | 18-04-23 06:30 | 18-04-23 06:00 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 This is to confirm that ForceClosureException_CoreCharges.cmd has been updated correctly. Job ran @ 23:00 Monday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 75 | N | 14.1:(466045) | None | None
14.2:(S3 VPN Big Pipe SoE) | Task | Imp | 14.2 | None | None | 0h 30m | 18-04-23 06:00 | 18-04-23 06:30 | 18-04-23 06:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 This is to confirm that IntegrationInstruction_DHReporting.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 76 | N | 14.2:(466045) | None | None
14.3:(S3 VPN Big Pipe SoE) | Task | Imp | 14.3 | None | None | 0h 30m | 18-04-23 07:45 | 18-04-23 08:15 | 18-04-23 07:45 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 This is to confirm that SSIS Package ForceClosureException_CoreAccounting.dtsx has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 77 | N | 14.3:(466045) | None | None
14.4:(S3 VPN Big Pipe SoE) | Task | Imp | 14.4 | None | None | 0h 30m | 18-04-23 08:00 | 18-04-23 08:30 | 18-04-23 08:00 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 This is to confirm that OverDraftLimit_SendIntegrationInstructions.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 78 | N | 14.4:(466045) | None | None
14.5:(S3 VPN Big Pipe SoE) | Task | Imp | 14.5 | None | None | 0h 30m | 18-04-23 08:30 | 18-04-23 09:00 | 18-04-23 08:30 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 This is to confirm that IntegrationInstruction_IncludeInClosureLetter4.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 79 | N | 14.5:(466045) | None | None
14.6:(S3 VPN Big Pipe SoE) | Task | Imp | 14.6 | None | None | 0h 30m | 18-04-23 09:00 | 18-04-23 09:30 | 18-04-23 09:00 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 This is to confirm that OverDraftLimit_CaptureFeedback_DH_D365.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 80 | N | 14.6:(466045) | None | None
14.7:(S3 VPN Big Pipe SoE) | Task | Imp | 14.7 | None | None | 0h 30m | 18-04-23 09:30 | 18-04-23 10:00 | 18-04-23 09:30 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 This is to confirm that IntegrationInstructionsR3_CoreAccounting.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 81 | N | 14.7:(466045) | None | None
14.8:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 14.8 | None | None | 0h 00m | 18-04-23 10:00 | 18-04-23 10:00 | - | Monitoring - Group 2 Tuesday | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 82 | N | 14.8:(466045) | None | None
15.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 15.0 | None | None | 0h 10m | 18-04-23 07:30 | 18-04-23 07:40 | - | cmd file Deployments - Tuesday 07:30 |  |  |  | Shape:Name=Deploy cmd Files - Third Group Shape:Colour=48,84,150 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 83 | N | 15.0:(466045) | None | None
15.1:(S3 VPN Big Pipe SoE) | Task | Imp | 15.1 | None | FS-15.2:(S3 VPN Big Pipe SoE) | 0h 05m | 18-04-23 07:30 | 18-04-23 07:35 | 18-04-23 07:30 | Dynamics - Copy cmd files to Production |  | EE and D365 | Dynamics - Copy cmd files to Production in folder /SSISPackages/Command MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd If any of the jobs are experiencing issues or running longer than expected, delay the change for the job until appropriate. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 84 | N | 15.1:(466045) | None | FS-15.2:(466045)
15.2:(S3 VPN Big Pipe SoE) | Task | Imp | 15.2 | FS-15.1:(S3 VPN Big Pipe SoE) | None | 0h 05m | 18-04-23 07:35 | 18-04-23 07:40 | - | Dynamics - Confirm cmd file changes Successfully Deployed |  | EE and D365 | Dynamics - Confirm cmd file changes Successfully Deployed in folder /SSISPackages/Command MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 85 | N | 15.2:(466045) | FS-15.1:(466045) | None
15.3:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 15.3 | None | None | 0h 00m | 18-04-23 07:40 | 18-04-23 07:40 | - | cmd file Deployments - Tuesday 07:30 | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 86 | N | 15.3:(466045) | None | None
16.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 16.0 | None | None | 8h 25m | 18-04-23 09:05 | 18-04-23 17:30 | - | Monitoring - Group 3 Tuesday |  |  |  | Shape:Name=Enhanced Job Monitoring - Third Group Shape:Colour=48,84,150 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 87 | N | 16.0:(466045) | None | None
16.1:(S3 VPN Big Pipe SoE) | Task | Imp | 16.1 | None | None | 8h 00m | 18-04-23 09:05 | 18-04-23 17:05 | 18-04-23 09:05 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 This is to confirm that MasterDataLoad.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 88 | N | 16.1:(466045) | None | None
16.2:(S3 VPN Big Pipe SoE) | Task | Imp | 16.2 | None | None | 0h 30m | 18-04-23 16:00 | 18-04-23 16:30 | 18-04-23 16:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 This is to confirm that IntegrationInstruction_DHRingfenced.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 89 | N | 16.2:(466045) | None | None
16.3:(S3 VPN Big Pipe SoE) | Task | Imp | 16.3 | None | None | 0h 30m | 18-04-23 16:00 | 18-04-23 16:30 | 18-04-23 16:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 This is to confirm that IntegrationInstruction_BOTClosureRetail.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 90 | N | 16.3:(466045) | None | None
16.4:(S3 VPN Big Pipe SoE) | Task | Imp | 16.4 | None | None | 0h 30m | 18-04-23 16:00 | 18-04-23 16:30 | 18-04-23 16:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 This is to confirm that IntegrationInstruction_BOTClosureCommercial.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 91 | N | 16.4:(466045) | None | None
16.5:(S3 VPN Big Pipe SoE) | Task | Imp | 16.5 | None | None | 0h 30m | 18-04-23 17:00 | 18-04-23 17:30 | 18-04-23 17:00 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 This is to confirm that GoneAway_Case_Closed_D365_to_DH.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 92 | N | 16.5:(466045) | None | None
16.6:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 16.6 | None | None | 0h 00m | 18-04-23 17:30 | 18-04-23 17:30 | - | Monitoring - Group 3 Tuesday | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 93 | N | 16.6:(466045) | None | None
17.0:(S3 VPN Big Pipe SoE) | Stage | Imp | 17.0 | None | None | 0h 30m | 19-04-23 08:00 | 19-04-23 08:30 | - | Monitoring - Group 3 Wednesday |  |  |  | Shape:Name=Enhanced Job Monitoring - Third Group Shape:Colour=48,84,150 |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 94 | N | 17.0:(466045) | None | None
17.1:(S3 VPN Big Pipe SoE) | Task | Imp | 17.1 | None | None | 0h 30m | 19-04-23 08:00 | 19-04-23 08:30 | 19-04-23 08:00 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 This is to confirm that DH_AccountRingfenced.cmd has been updated correctly. Job ran 19:00 Tuesday evening. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 95 | N | 17.1:(466045) | None | None
17.2:(S3 VPN Big Pipe SoE) | Task | Imp | 17.2 | None | None | 0h 30m | 19-04-23 08:00 | 19-04-23 08:30 | 19-04-23 08:00 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 This is to confirm that CommunicationCycles.cmd has been updated correctly. Job ran 22:00 Tuesday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 96 | N | 17.2:(466045) | None | None
17.3:(S3 VPN Big Pipe SoE) | Checkpoint | Imp | 17.3 | None | None | 0h 00m | 19-04-23 08:30 | 19-04-23 08:30 | - | Monitoring - Group 3 Wednesday | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 97 | N | 17.3:(466045) | None | None
18.0:(S3 VPN Big Pipe SoE) | Stage | Post | 18.0 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Implementation Stand-down | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 98 | N | 18.0:(466045) | None | None
18.1:(S3 VPN Big Pipe SoE) | Task | Post | 18.1 | None | None | 0h 00m | 19-04-23 08:30 | 19-04-23 08:30 | - | Milestone - Implementation Complete |  | Implementation Manager |  |  |  | S3 VPN Big Pipe SoE | 466045 | Y |  |  |  |  | Review | 99 | N | 18.1:(466045) | None | None
18.2:(S3 VPN Big Pipe SoE) | Task | Post | 18.2 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Confirm Final Go Decision |  | Implementation Manager |  |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 100 | N | 18.2:(466045) | None | None
18.3:(S3 VPN Big Pipe SoE) | Task | Post | 18.3 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Send Comms - Implementation Successfully Completed |  | Implementation Manager |  |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 101 | N | 18.3:(466045) | None | None
18.4:(S3 VPN Big Pipe SoE) | Task | Post | 18.4 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Inform SysOps that change has completed if necessary |  | Implementation Manager | Inform SysOps that change has completed if necessary Use email sent for start of change to inform sysops we are complete |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 102 | N | 18.4:(466045) | None | None
18.5:(S3 VPN Big Pipe SoE) | Checkpoint | Post | 18.5 | None | None | 0h 00m | 19-04-23 08:45 | 19-04-23 08:45 | - | Implementation Stand-down | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 103 | N | 18.5:(466045) | None | None
19.0:(S3 VPN Big Pipe SoE) | Stage | Post | 19.0 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Post Implementation Tidy Up | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Pre-Activated | 104 | N | 19.0:(466045) | None | None
19.1:(S3 VPN Big Pipe SoE) | Task | Post | 19.1 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Gather Dynamics Checkout Evidence for MCR |  | Implementation Manager | Gather Testing evidence and attached to Change record |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 105 | N | 19.1:(466045) | None | None
19.2:(S3 VPN Big Pipe SoE) | Task | Post | 19.2 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Close Dynamics TCR |  | EE Team |  |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 106 | N | 19.2:(466045) | None | None
19.3:(S3 VPN Big Pipe SoE) | Task | Post | 19.3 | None | None | 0h 15m | 19-04-23 08:30 | 19-04-23 08:45 | - | Close MCR |  | Implementation Manager | Gather testing evidence and attach to MCR |  |  | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 107 | N | 19.3:(466045) | None | None
19.4:(S3 VPN Big Pipe SoE) | Checkpoint | Post | 19.4 | None | None | 0h 00m | 19-04-23 08:45 | 19-04-23 08:45 | - | Post Implementation Tidy Up | [5 empty] | S3 VPN Big Pipe SoE | 466045 | N |  |  |  |  | Review | 108 | N | 19.4:(466045) | None | None

## Event SoE
Task Identifier |  |  | Timings |  |  |  |  | Task Information | [7 empty] | Filters |  |  |  | ICEFLO SoE Information
Task Type | Event Task Id (EVT ID) | SoE Id (ID) | Duration | Expicit Start Time | Start Time | End Time | Team | Title | Description | Tech Detail | Skip | Predecessors (EVT Id) | Predecessors Expanded | Successors (EVT Id) | Successors Expanded | User Defined 1 | User Defined 2 | User Defined 3 | User Defined 4 | SoE Name | SoE Number
Stage | 1:(S3 VPN Big Pipe SoE) | 1.0:(S3 VPN Big Pipe SoE) | 1h 00m | - | 14-04-23 09:00 | 14-04-23 10:00 |  | Pre-Implementation Access and Backup Activities |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 2:(S3 VPN Big Pipe SoE) | 1.1:(S3 VPN Big Pipe SoE) | 1h 00m | 14-04-23 09:00 | 14-04-23 09:00 | 14-04-23 10:00 | D365 | Confirm Dynamics Team access has been requested and granted |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 3:(S3 VPN Big Pipe SoE) | 1.2:(S3 VPN Big Pipe SoE) | 1h 00m | 14-04-23 09:00 | 14-04-23 09:00 | 14-04-23 10:00 | Implementation Manager | Confirm D365 Autosys ReadOnly access requested | Confirm D365 Autosys ReadOnly access requested for Implementation Manager |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 4:(S3 VPN Big Pipe SoE) | 1.3:(S3 VPN Big Pipe SoE) | 1h 00m | 14-04-23 09:00 | 14-04-23 09:00 | 14-04-23 10:00 | EE Team | Confirm EE Team have requested all the required accesses | Confirm EE Team have requested all the required accesses Autosys access etc Ensure access is granted for Service Account Service-Crmwdlprdapi to allow deployment of the Solution |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 5:(S3 VPN Big Pipe SoE) | 1.4:(S3 VPN Big Pipe SoE) | 1h 00m | 14-04-23 09:00 | 14-04-23 09:00 | 14-04-23 10:00 | EE Team | EE Team to check Production Servers have sufficient space | EE Team to check Production Servers have sufficient space If there are any any issues with space on the Production server raise appropriate tickets to tidy up |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 6:(S3 VPN Big Pipe SoE) | 1.5:(S3 VPN Big Pipe SoE) | 1h 00m | 14-04-23 09:00 | 14-04-23 09:00 | 14-04-23 10:00 | Implementation Manager | Confirm all Firewall changes are complete |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 7:(S3 VPN Big Pipe SoE) | 1.6:(S3 VPN Big Pipe SoE) | 0h 00m | - | 14-04-23 10:00 | 14-04-23 10:00 |  | Pre-Implementation Access and Backup Activities |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 8:(S3 VPN Big Pipe SoE) | 2.0:(S3 VPN Big Pipe SoE) | 0h 10m | - | 16-04-23 08:30 | 16-04-23 08:40 |  | Implementation Readiness |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 9:(S3 VPN Big Pipe SoE) | 2.1:(S3 VPN Big Pipe SoE) | 0h 00m | 16-04-23 08:30 | 16-04-23 08:30 | 16-04-23 08:30 | Implementation Manager | Start Implementation Time - 04:00 Friday |  |  | Y | None | None | FS-11:(S3 VPN Big Pipe SoE), FS-12:(S3 VPN Big Pipe SoE), FS-10:(S3 VPN Big Pipe SoE) | FS-11:(S3 VPN Big Pipe SoE):{Inform System Operations that the implementation is about to Start}, FS-12:(S3 VPN Big Pipe SoE):{Check MCR MCR1292210 is set to SCHEDULED}, FS-10:(S3 VPN Big Pipe SoE):{Open Command and Control Line and Teams Group Chat} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 10:(S3 VPN Big Pipe SoE) | 2.2:(S3 VPN Big Pipe SoE) | 0h 10m | - | 16-04-23 08:30 | 16-04-23 08:40 | Implementation Manager | Open Command and Control Line and Teams Group Chat | Zoom - 7887 505 808 Open Teams Group Chat for implementation and invite all resources |  | N | FS-9:(S3 VPN Big Pipe SoE) | FS-9:(S3 VPN Big Pipe SoE):[Start Implementation Time - 04:00 Friday] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 11:(S3 VPN Big Pipe SoE) | 2.3:(S3 VPN Big Pipe SoE) | 0h 10m | - | 16-04-23 08:30 | 16-04-23 08:40 | Implementation Manager | Inform System Operations that the implementation is about to Start | Inform System Operations that the implementation is about to start CONFIRMING THERE ARE NO KNOWN ISSUES which would prevent this implementation from starting. Send mail to ~ System Operations Offhost <fpitopm@natwest.com> ~ System Operations Mainframe <system.operations@rbs.co.uk> Sys Ops Off-Host: +44 131 626 6540 Sys Ops Mainframe : +44 131 626 6510 Also check the P1 / P2 Incident Dashboard | https://rbos.service-now.com/now/nav/ui/classic/params/target/%24pa_dashboard.do%3Fsysparm_dashboard%3D770beb991bec5550adf5a8e6b04bcb4b | N | FS-9:(S3 VPN Big Pipe SoE) | FS-9:(S3 VPN Big Pipe SoE):[Start Implementation Time - 04:00 Friday] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 12:(S3 VPN Big Pipe SoE) | 2.4:(S3 VPN Big Pipe SoE) | 0h 10m | - | 16-04-23 08:30 | 16-04-23 08:40 | Implementation Manager | Check MCR MCR1292210 is set to SCHEDULED |  |  | N | FS-9:(S3 VPN Big Pipe SoE) | FS-9:(S3 VPN Big Pipe SoE):[Start Implementation Time - 04:00 Friday] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 13:(S3 VPN Big Pipe SoE) | 2.5:(S3 VPN Big Pipe SoE) | 0h 00m | - | 16-04-23 08:40 | 16-04-23 08:40 |  | Implementation Readiness |  |  | N | None | None | FS-15:(S3 VPN Big Pipe SoE) | FS-15:(S3 VPN Big Pipe SoE):{Perform Curl to confirm connections are in place} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 14:(S3 VPN Big Pipe SoE) | 3.0:(S3 VPN Big Pipe SoE) | 0h 05m | - | 16-04-23 09:00 | 16-04-23 09:05 |  | Readiness Check |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 15:(S3 VPN Big Pipe SoE) | 3.1:(S3 VPN Big Pipe SoE) | 0h 05m | 16-04-23 09:00 | 16-04-23 09:00 | 16-04-23 09:05 |  | Perform Curl to confirm connections are in place | Perform Curl to confirm connections are in place |  | N | FS-13:(S3 VPN Big Pipe SoE) | FS-13:(S3 VPN Big Pipe SoE):[Implementation Readiness] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 16:(S3 VPN Big Pipe SoE) | 3.2:(S3 VPN Big Pipe SoE) | 0h 00m | - | 16-04-23 09:05 | 16-04-23 09:05 |  | Readiness Check |  |  | N | None | None | FS-18:(S3 VPN Big Pipe SoE) | FS-18:(S3 VPN Big Pipe SoE):{Internal Checkpoint - Connectivity Confirmed - Start Changes} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 17:(S3 VPN Big Pipe SoE) | 4.0:(S3 VPN Big Pipe SoE) | 0h 00m | - | 16-04-23 09:05 | 16-04-23 09:05 |  | Milestone - Connectivity Confirmed |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 18:(S3 VPN Big Pipe SoE) | 4.1:(S3 VPN Big Pipe SoE) | 0h 00m | - | 16-04-23 09:05 | 16-04-23 09:05 | Implementation Manager | Internal Checkpoint - Connectivity Confirmed - Start Changes |  |  | Y | FS-16:(S3 VPN Big Pipe SoE) | FS-16:(S3 VPN Big Pipe SoE):[Readiness Check] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 19:(S3 VPN Big Pipe SoE) | 4.2:(S3 VPN Big Pipe SoE) | 0h 00m | - | 16-04-23 09:05 | 16-04-23 09:05 |  | Milestone - Connectivity Confirmed |  |  | N | None | None | FS-21:(S3 VPN Big Pipe SoE) | FS-21:(S3 VPN Big Pipe SoE):{EE Team - ON ICE Jobs} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 20:(S3 VPN Big Pipe SoE) | 5.0:(S3 VPN Big Pipe SoE) | 0h 10m | - | 16-04-23 09:05 | 16-04-23 09:15 |  | ON ICE AutoSys Jobs before changes - Sunday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 21:(S3 VPN Big Pipe SoE) | 5.1:(S3 VPN Big Pipe SoE) | 0h 05m | - | 16-04-23 09:05 | 16-04-23 09:10 | EE and D365 | EE Team - ON ICE Jobs | EE Team - ON ICE Jobs Place following boxes ON ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Place following jobs ON ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | N | FS-19:(S3 VPN Big Pipe SoE) | FS-19:(S3 VPN Big Pipe SoE):[Milestone - Connectivity Confirmed] | FS-22:(S3 VPN Big Pipe SoE) | FS-22:(S3 VPN Big Pipe SoE):{EE Team - Verfiy Jobs have been placed ON ICE} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 22:(S3 VPN Big Pipe SoE) | 5.2:(S3 VPN Big Pipe SoE) | 0h 05m | - | 16-04-23 09:10 | 16-04-23 09:15 | EE and D365 | EE Team - Verfiy Jobs have been placed ON ICE | EE Team - Verfiy Jobs have been placed ON ICE Confirm following boxes ON ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Confirm following jobs ON ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | N | FS-21:(S3 VPN Big Pipe SoE) | FS-21:(S3 VPN Big Pipe SoE):[EE Team - ON ICE Jobs] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 23:(S3 VPN Big Pipe SoE) | 5.3:(S3 VPN Big Pipe SoE) | 0h 00m | - | 16-04-23 09:15 | 16-04-23 09:15 |  | ON ICE AutoSys Jobs before changes - Sunday |  |  | N | None | None | FS-25:(S3 VPN Big Pipe SoE) | FS-25:(S3 VPN Big Pipe SoE):{Dynamics - Create Backout Restore point - Dynamics SSIS Packages and cmd file Copy} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 24:(S3 VPN Big Pipe SoE) | 6.0:(S3 VPN Big Pipe SoE) | 0h 15m | - | 17-04-23 04:00 | 17-04-23 04:15 |  | cmd file Deployments - Monday 04:00 |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 25:(S3 VPN Big Pipe SoE) | 6.1:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 04:00 | 17-04-23 04:00 | 17-04-23 04:05 | EE and D365 | Dynamics - Create Backout Restore point - Dynamics SSIS Packages and cmd file Copy | Dynamics - Create Backout Restore point - Dynamics SSIS Packages and cmd file Copy In production server backup all files in folders: /SSISPackages/Command /SSISPackages/DTX Specifically take backups of the following SSIS Package files: IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx |  | N | FS-23:(S3 VPN Big Pipe SoE) | FS-23:(S3 VPN Big Pipe SoE):[ON ICE AutoSys Jobs before changes - Sunday] | FS-26:(S3 VPN Big Pipe SoE) | FS-26:(S3 VPN Big Pipe SoE):{Dynamics - Copy SSIS Packages and cmd files to Production} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 26:(S3 VPN Big Pipe SoE) | 6.2:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:05 | 17-04-23 04:10 | EE and D365 | Dynamics - Copy SSIS Packages and cmd files to Production | Dynamics - Copy SSIS Packages and cmd files to Production in folder /SSISPackages/Command IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd in folder /SSISPackages/DTX IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx |  | N | FS-25:(S3 VPN Big Pipe SoE) | FS-25:(S3 VPN Big Pipe SoE):[Dynamics - Create Backout Restore point - Dynamics SSIS Packages and cmd file Copy] | FS-27:(S3 VPN Big Pipe SoE) | FS-27:(S3 VPN Big Pipe SoE):{Dynamics - Confirm SSIS Package and cmd file changes Successfully Deployed} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 27:(S3 VPN Big Pipe SoE) | 6.3:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:10 | 17-04-23 04:15 | EE and D365 | Dynamics - Confirm SSIS Package and cmd file changes Successfully Deployed | Dynamics - Confirm SSIS Package and cmd file changes Successfully Deployed Confirm in folder /SSISPackages/Command IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd Confirm in folder /SSISPackages/DTX IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-26:(S3 VPN Big Pipe SoE) | FS-26:(S3 VPN Big Pipe SoE):[Dynamics - Copy SSIS Packages and cmd files to Production] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 28:(S3 VPN Big Pipe SoE) | 6.4:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 04:15 | 17-04-23 04:15 |  | cmd file Deployments - Monday 04:00 |  |  | N | None | None | FS-30:(S3 VPN Big Pipe SoE) | FS-30:(S3 VPN Big Pipe SoE):{Dynamics - Force Start msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 29:(S3 VPN Big Pipe SoE) | 7.0:(S3 VPN Big Pipe SoE) | 0h 45m | - | 17-04-23 04:15 | 17-04-23 05:00 |  | Adhoc Job runs to prove Autosys Setup |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 30:(S3 VPN Big Pipe SoE) | 7.1:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:15 | 17-04-23 04:20 | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 | Dynamics - Force Start msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-28:(S3 VPN Big Pipe SoE) | FS-28:(S3 VPN Big Pipe SoE):[cmd file Deployments - Monday 04:00] | FS-31:(S3 VPN Big Pipe SoE) | FS-31:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 31:(S3 VPN Big Pipe SoE) | 7.2:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:20 | 17-04-23 04:25 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-30:(S3 VPN Big Pipe SoE) | FS-30:(S3 VPN Big Pipe SoE):[Dynamics - Force Start msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1] | FS-32:(S3 VPN Big Pipe SoE) | FS-32:(S3 VPN Big Pipe SoE):{Dynamics - Force Start msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 32:(S3 VPN Big Pipe SoE) | 7.3:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:25 | 17-04-23 04:30 | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 | Dynamics - Force Start msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-31:(S3 VPN Big Pipe SoE) | FS-31:(S3 VPN Big Pipe SoE):[Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1] | FS-33:(S3 VPN Big Pipe SoE) | FS-33:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 33:(S3 VPN Big Pipe SoE) | 7.4:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:30 | 17-04-23 04:35 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-32:(S3 VPN Big Pipe SoE) | FS-32:(S3 VPN Big Pipe SoE):[Dynamics - Force Start msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1] | FS-34:(S3 VPN Big Pipe SoE) | FS-34:(S3 VPN Big Pipe SoE):{Dynamics - Force Start msd.edi.prd.wdl.spinotebox.ep1} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 34:(S3 VPN Big Pipe SoE) | 7.5:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:35 | 17-04-23 04:40 | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.spinotebox.ep1 | Dynamics - Force Start msd.edi.prd.wdl.spinotebox.ep1 On completion of msd.edi.prd.wdl.integrationinstructionspinote.ep1 the job msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 should run Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-33:(S3 VPN Big Pipe SoE) | FS-33:(S3 VPN Big Pipe SoE):[Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1] | FS-35:(S3 VPN Big Pipe SoE) | FS-35:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - Confirm both SPI Note jobs run as expected} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 35:(S3 VPN Big Pipe SoE) | 7.6:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:40 | 17-04-23 04:45 | EE and D365 | Dynamics Technical Check - Confirm both SPI Note jobs run as expected | Dynamics Technical Check - Confirm both SPI Note jobs run as expected msd.edi.prd.wdl.integrationinstructionspinote.ep1 msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-34:(S3 VPN Big Pipe SoE) | FS-34:(S3 VPN Big Pipe SoE):[Dynamics - Force Start msd.edi.prd.wdl.spinotebox.ep1] | FS-36:(S3 VPN Big Pipe SoE) | FS-36:(S3 VPN Big Pipe SoE):{Dynamics - Force Start msd.edi.prd.wdl.cohorttranchebox.ep1} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 36:(S3 VPN Big Pipe SoE) | 7.7:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:45 | 17-04-23 04:50 | EE and D365 | Dynamics - Force Start msd.edi.prd.wdl.cohorttranchebox.ep1 | Dynamics - Force Start msd.edi.prd.wdl.cohorttranchebox.ep1 On completion of msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 the job msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 should run Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-35:(S3 VPN Big Pipe SoE) | FS-35:(S3 VPN Big Pipe SoE):[Dynamics Technical Check - Confirm both SPI Note jobs run as expected] | FS-37:(S3 VPN Big Pipe SoE) | FS-37:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - Confirm both Cohort Tranche jobs run as expected} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 37:(S3 VPN Big Pipe SoE) | 7.8:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:50 | 17-04-23 04:55 | EE and D365 | Dynamics Technical Check - Confirm both Cohort Tranche jobs run as expected | Dynamics Technical Check - Confirm both Cohort Tranche jobs run as expected msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 Confirm Job has completed successfully and produced the expected output. Record any output which has been created that is not being tidied up for future reference in Business Checkout Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-36:(S3 VPN Big Pipe SoE) | FS-36:(S3 VPN Big Pipe SoE):[Dynamics - Force Start msd.edi.prd.wdl.cohorttranchebox.ep1] | FS-38:(S3 VPN Big Pipe SoE) | FS-38:(S3 VPN Big Pipe SoE):{DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during job checkout} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 38:(S3 VPN Big Pipe SoE) | 7.9:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 04:55 | 17-04-23 05:00 | EE and D365 | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during job checkout | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during job checkout Confirm data received on DataHub for the following jobs runs: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 msd.edi.prd.wdl.integrationinstructionspinote.ep1 msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 These jobs run hourly Monday to Friday, continue monitoring until we are happy data is being received. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-37:(S3 VPN Big Pipe SoE) | FS-37:(S3 VPN Big Pipe SoE):[Dynamics Technical Check - Confirm both Cohort Tranche jobs run as expected] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 39:(S3 VPN Big Pipe SoE) | 7.10:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 05:00 | 17-04-23 05:00 |  | Adhoc Job runs to prove Autosys Setup |  |  | N | None | None | FS-41:(S3 VPN Big Pipe SoE) | FS-41:(S3 VPN Big Pipe SoE):{EE Team - OFF ICE Jobs} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 40:(S3 VPN Big Pipe SoE) | 8.0:(S3 VPN Big Pipe SoE) | 0h 20m | - | 17-04-23 05:00 | 17-04-23 05:20 |  | OFF ICE AutoSys Jobs after changes - Return to BAU |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 41:(S3 VPN Big Pipe SoE) | 8.1:(S3 VPN Big Pipe SoE) | 0h 10m | - | 17-04-23 05:00 | 17-04-23 05:10 | EE and D365 | EE Team - OFF ICE Jobs | EE Team - OFF ICE Jobs Place following boxes OFF ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Place following jobs OFF ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | N | FS-39:(S3 VPN Big Pipe SoE) | FS-39:(S3 VPN Big Pipe SoE):[Adhoc Job runs to prove Autosys Setup] | FS-42:(S3 VPN Big Pipe SoE) | FS-42:(S3 VPN Big Pipe SoE):{EE Team - Verfiy Jobs have been placed OFF ICE} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 42:(S3 VPN Big Pipe SoE) | 8.2:(S3 VPN Big Pipe SoE) | 0h 10m | - | 17-04-23 05:10 | 17-04-23 05:20 | EE and D365 | EE Team - Verfiy Jobs have been placed OFF ICE | EE Team - Verfiy Jobs have been placed OFF ICE Confirm following boxes OFF ICE: msd.edi.prd.wdl.spinotebox.ep1 msd.edi.prd.wdl.cohorttranchebox.ep1 Confirm following jobs OFF ICE: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | N | FS-41:(S3 VPN Big Pipe SoE) | FS-41:(S3 VPN Big Pipe SoE):[EE Team - OFF ICE Jobs] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 43:(S3 VPN Big Pipe SoE) | 8.3:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 05:20 | 17-04-23 05:20 |  | OFF ICE AutoSys Jobs after changes - Return to BAU |  |  | N | None | None | FS-45:(S3 VPN Big Pipe SoE) | FS-45:(S3 VPN Big Pipe SoE):{Internal Checkpoint - All Code Deployments Complete} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 44:(S3 VPN Big Pipe SoE) | 9.0:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 05:20 | 17-04-23 05:20 |  | Milestone - Deployments Complete |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 45:(S3 VPN Big Pipe SoE) | 9.1:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 05:20 | 17-04-23 05:20 | Implementation Manager | Internal Checkpoint - All Code Deployments Complete |  |  | Y | FS-43:(S3 VPN Big Pipe SoE) | FS-43:(S3 VPN Big Pipe SoE):[OFF ICE AutoSys Jobs after changes - Return to BAU] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 46:(S3 VPN Big Pipe SoE) | 9.2:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 05:20 | 17-04-23 05:20 |  | Milestone - Deployments Complete |  |  | N | None | None | FS-52:(S3 VPN Big Pipe SoE), FS-48:(S3 VPN Big Pipe SoE), FS-49:(S3 VPN Big Pipe SoE), FS-50:(S3 VPN Big Pipe SoE), FS-51:(S3 VPN Big Pipe SoE), FS-53:(S3 VPN Big Pipe SoE), FS-54:(S3 VPN Big Pipe SoE) | FS-52:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1}, FS-48:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1}, FS-49:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1}, FS-50:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1}, FS-51:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1}, FS-53:(S3 VPN Big Pipe SoE):{Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1}, FS-54:(S3 VPN Big Pipe SoE):{DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during Monitoring} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 47:(S3 VPN Big Pipe SoE) | 10.0:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 |  | Monday Job Monitoring |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 48:(S3 VPN Big Pipe SoE) | 10.1:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-46:(S3 VPN Big Pipe SoE) | FS-46:(S3 VPN Big Pipe SoE):[Milestone - Deployments Complete] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 49:(S3 VPN Big Pipe SoE) | 10.2:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 CUSTRM-72540 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-46:(S3 VPN Big Pipe SoE) | FS-46:(S3 VPN Big Pipe SoE):[Milestone - Deployments Complete] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 50:(S3 VPN Big Pipe SoE) | 10.3:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Job runs Daily - MTWTF - Hourly on xx:25 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-46:(S3 VPN Big Pipe SoE) | FS-46:(S3 VPN Big Pipe SoE):[Milestone - Deployments Complete] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 51:(S3 VPN Big Pipe SoE) | 10.4:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Job runs Daily - MTWTF - Hourly on xx:40 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-46:(S3 VPN Big Pipe SoE) | FS-46:(S3 VPN Big Pipe SoE):[Milestone - Deployments Complete] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 52:(S3 VPN Big Pipe SoE) | 10.5:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-46:(S3 VPN Big Pipe SoE) | FS-46:(S3 VPN Big Pipe SoE):[Milestone - Deployments Complete] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 53:(S3 VPN Big Pipe SoE) | 10.6:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.integrationinstructionspinote.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | FS-46:(S3 VPN Big Pipe SoE) | FS-46:(S3 VPN Big Pipe SoE):[Milestone - Deployments Complete] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 54:(S3 VPN Big Pipe SoE) | 10.7:(S3 VPN Big Pipe SoE) | 6h 00m | - | 17-04-23 05:20 | 17-04-23 11:20 | DataHub | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during Monitoring | DataHub Technical Check - Confirm IntegrationInstruction Jobs Data Received during Monitoring Confirm data received on DataHub for the following jobs runs: msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 msd.edi.prd.wdl.integrationinstructionspinote.ep1 msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 These jobs run hourly Monday to Friday, continue monitoring until we are happy data is being received. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-46:(S3 VPN Big Pipe SoE) | FS-46:(S3 VPN Big Pipe SoE):[Milestone - Deployments Complete] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 55:(S3 VPN Big Pipe SoE) | 10.8:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 11:20 | 17-04-23 11:20 |  | Monday Job Monitoring |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 56:(S3 VPN Big Pipe SoE) | 11.0:(S3 VPN Big Pipe SoE) | 1h 00m | - | 17-04-23 12:00 | 17-04-23 13:00 |  | cmd file Deployments - Monday 12.00 |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 57:(S3 VPN Big Pipe SoE) | 11.1:(S3 VPN Big Pipe SoE) | 0h 10m | 17-04-23 12:00 | 17-04-23 12:00 | 17-04-23 12:10 | EE and D365 | EE Team - Confirm msd.edi.prd.wdl.tranchesd365todh.ep1 not running | EE Team - Confirm msd.edi.prd.wdl.tranchesd365todh.ep1 not running Job runs hourly at 55 minutes passed the hour. Ensure that the 11:55 job has completed and is not running before continuing. If there are issues with the job or it is running longer than expected this can be delayed until it is appropriate to perform the changes |  | N | None | None | FS-58:(S3 VPN Big Pipe SoE) | FS-58:(S3 VPN Big Pipe SoE):{EE Team - ON ICE Jobs} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 58:(S3 VPN Big Pipe SoE) | 11.2:(S3 VPN Big Pipe SoE) | 0h 10m | - | 17-04-23 12:10 | 17-04-23 12:20 | EE and D365 | EE Team - ON ICE Jobs | EE Team - ON ICE Jobs msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  | N | FS-57:(S3 VPN Big Pipe SoE) | FS-57:(S3 VPN Big Pipe SoE):[EE Team - Confirm msd.edi.prd.wdl.tranchesd365todh.ep1 not running] | FS-59:(S3 VPN Big Pipe SoE) | FS-59:(S3 VPN Big Pipe SoE):{EE Team - Verfiy Jobs have been placed ON ICE} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 59:(S3 VPN Big Pipe SoE) | 11.3:(S3 VPN Big Pipe SoE) | 0h 10m | - | 17-04-23 12:20 | 17-04-23 12:30 | EE and D365 | EE Team - Verfiy Jobs have been placed ON ICE | EE Team - Verify Jobs have been placed ON ICE Confirm following job is ON ICE: msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  | N | FS-58:(S3 VPN Big Pipe SoE) | FS-58:(S3 VPN Big Pipe SoE):[EE Team - ON ICE Jobs] | FS-60:(S3 VPN Big Pipe SoE) | FS-60:(S3 VPN Big Pipe SoE):{Dynamics - Copy cmd files to Production} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 60:(S3 VPN Big Pipe SoE) | 11.4:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 12:30 | 17-04-23 12:35 | EE and D365 | Dynamics - Copy cmd files to Production | Dynamics - Copy cmd files to Production in folder /SSISPackages/Command Tranches_D365_to_DH.cmd |  | N | FS-59:(S3 VPN Big Pipe SoE) | FS-59:(S3 VPN Big Pipe SoE):[EE Team - Verfiy Jobs have been placed ON ICE] | FS-61:(S3 VPN Big Pipe SoE) | FS-61:(S3 VPN Big Pipe SoE):{Dynamics - Confirm cmd file changes Successfully Deployed} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 61:(S3 VPN Big Pipe SoE) | 11.5:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 12:35 | 17-04-23 12:40 | EE and D365 | Dynamics - Confirm cmd file changes Successfully Deployed | Dynamics - Confirm cmd file changes Successfully Deployed in folder /SSISPackages/Command Tranches_D365_to_DH.cmd Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-60:(S3 VPN Big Pipe SoE) | FS-60:(S3 VPN Big Pipe SoE):[Dynamics - Copy cmd files to Production] | FS-62:(S3 VPN Big Pipe SoE) | FS-62:(S3 VPN Big Pipe SoE):{EE Team - OFF ICE Jobs} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 62:(S3 VPN Big Pipe SoE) | 11.6:(S3 VPN Big Pipe SoE) | 0h 10m | - | 17-04-23 12:40 | 17-04-23 12:50 | EE and D365 | EE Team - OFF ICE Jobs | EE Team - OFF ICE Jobs msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  | N | FS-61:(S3 VPN Big Pipe SoE) | FS-61:(S3 VPN Big Pipe SoE):[Dynamics - Confirm cmd file changes Successfully Deployed] | FS-63:(S3 VPN Big Pipe SoE) | FS-63:(S3 VPN Big Pipe SoE):{EE Team - Verfiy Jobs have been placed OFF ICE} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 63:(S3 VPN Big Pipe SoE) | 11.7:(S3 VPN Big Pipe SoE) | 0h 10m | - | 17-04-23 12:50 | 17-04-23 13:00 | EE and D365 | EE Team - Verfiy Jobs have been placed OFF ICE | EE Team - Verfiy Jobs have been placed OFF ICE Confirm following job is OFF ICE: msd.edi.prd.wdl.tranchesd365todh.ep1 This step can be skipped if there is sufficient time before the next run of the job at 55 mins passed the hour. |  | N | FS-62:(S3 VPN Big Pipe SoE) | FS-62:(S3 VPN Big Pipe SoE):[EE Team - OFF ICE Jobs] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 64:(S3 VPN Big Pipe SoE) | 11.8:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 13:00 | 17-04-23 13:00 |  | cmd file Deployments - Monday 12.00 |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 65:(S3 VPN Big Pipe SoE) | 12.0:(S3 VPN Big Pipe SoE) | 0h 10m | - | 17-04-23 12:00 | 17-04-23 12:10 |  | cmd file Deployments - Monday 12.00 |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 66:(S3 VPN Big Pipe SoE) | 12.1:(S3 VPN Big Pipe SoE) | 0h 05m | 17-04-23 12:00 | 17-04-23 12:00 | 17-04-23 12:05 | EE and D365 | Dynamics - Copy cmd files to Production | Dynamics - Copy cmd files to Production in folder /SSISPackages/Command IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd If any of the jobs are experiencing issues or running longer than expected, delay the change for the job until appropriate. |  | N | None | None | FS-67:(S3 VPN Big Pipe SoE) | FS-67:(S3 VPN Big Pipe SoE):{Dynamics - Confirm cmd file changes Successfully Deployed} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 67:(S3 VPN Big Pipe SoE) | 12.2:(S3 VPN Big Pipe SoE) | 0h 05m | - | 17-04-23 12:05 | 17-04-23 12:10 | EE and D365 | Dynamics - Confirm cmd file changes Successfully Deployed | Dynamics - Confirm cmd file changes Successfully Deployed in folder /SSISPackages/Command IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-66:(S3 VPN Big Pipe SoE) | FS-66:(S3 VPN Big Pipe SoE):[Dynamics - Copy cmd files to Production] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 68:(S3 VPN Big Pipe SoE) | 12.3:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 12:10 | 17-04-23 12:10 |  | cmd file Deployments - Monday 12.00 |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 69:(S3 VPN Big Pipe SoE) | 13.0:(S3 VPN Big Pipe SoE) | 8h 00m | - | 17-04-23 12:55 | 17-04-23 20:55 |  | Monitoring - Group 2 Monday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 70:(S3 VPN Big Pipe SoE) | 13.1:(S3 VPN Big Pipe SoE) | 8h 00m | 17-04-23 12:55 | 17-04-23 12:55 | 17-04-23 20:55 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 This is to confirm that Tranches_D365_to_DH.cmd has been updated correctly. This jobs runs hourly on 15 mins passed the hour. Keep monitoring this job until is is confirmed that job has processed data. This is a possibility that the job may not get any data to process on Monday, if this is the case continue monitoring on Tuesday as required. If we are struggling to confirm the job check with Dynamics and the Event Manager when to stop monitoring. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 71:(S3 VPN Big Pipe SoE) | 13.2:(S3 VPN Big Pipe SoE) | 0h 30m | 17-04-23 14:00 | 17-04-23 14:00 | 17-04-23 14:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 This is to confirm that IntegrationInstructionsR3_CoreCharges.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 72:(S3 VPN Big Pipe SoE) | 13.3:(S3 VPN Big Pipe SoE) | 0h 30m | 17-04-23 17:00 | 17-04-23 17:00 | 17-04-23 17:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 This is to confirm that SwitcherBOT_Commercial_D365_to_DH.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 73:(S3 VPN Big Pipe SoE) | 13.4:(S3 VPN Big Pipe SoE) | 0h 00m | - | 17-04-23 20:55 | 17-04-23 20:55 |  | Monitoring - Group 2 Monday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 74:(S3 VPN Big Pipe SoE) | 14.0:(S3 VPN Big Pipe SoE) | 4h 00m | - | 18-04-23 06:00 | 18-04-23 10:00 |  | Monitoring - Group 2 Tuesday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 75:(S3 VPN Big Pipe SoE) | 14.1:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 06:00 | 18-04-23 06:00 | 18-04-23 06:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 This is to confirm that ForceClosureException_CoreCharges.cmd has been updated correctly. Job ran @ 23:00 Monday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 76:(S3 VPN Big Pipe SoE) | 14.2:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 06:00 | 18-04-23 06:00 | 18-04-23 06:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 This is to confirm that IntegrationInstruction_DHReporting.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 77:(S3 VPN Big Pipe SoE) | 14.3:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 07:45 | 18-04-23 07:45 | 18-04-23 08:15 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 This is to confirm that SSIS Package ForceClosureException_CoreAccounting.dtsx has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 78:(S3 VPN Big Pipe SoE) | 14.4:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 08:00 | 18-04-23 08:00 | 18-04-23 08:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 This is to confirm that OverDraftLimit_SendIntegrationInstructions.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 79:(S3 VPN Big Pipe SoE) | 14.5:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 08:30 | 18-04-23 08:30 | 18-04-23 09:00 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 This is to confirm that IntegrationInstruction_IncludeInClosureLetter4.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 80:(S3 VPN Big Pipe SoE) | 14.6:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 09:00 | 18-04-23 09:00 | 18-04-23 09:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 This is to confirm that OverDraftLimit_CaptureFeedback_DH_D365.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 81:(S3 VPN Big Pipe SoE) | 14.7:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 09:30 | 18-04-23 09:30 | 18-04-23 10:00 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 This is to confirm that IntegrationInstructionsR3_CoreAccounting.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 82:(S3 VPN Big Pipe SoE) | 14.8:(S3 VPN Big Pipe SoE) | 0h 00m | - | 18-04-23 10:00 | 18-04-23 10:00 |  | Monitoring - Group 2 Tuesday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 83:(S3 VPN Big Pipe SoE) | 15.0:(S3 VPN Big Pipe SoE) | 0h 10m | - | 18-04-23 07:30 | 18-04-23 07:40 |  | cmd file Deployments - Tuesday 07:30 |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 84:(S3 VPN Big Pipe SoE) | 15.1:(S3 VPN Big Pipe SoE) | 0h 05m | 18-04-23 07:30 | 18-04-23 07:30 | 18-04-23 07:35 | EE and D365 | Dynamics - Copy cmd files to Production | Dynamics - Copy cmd files to Production in folder /SSISPackages/Command MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd If any of the jobs are experiencing issues or running longer than expected, delay the change for the job until appropriate. |  | N | None | None | FS-85:(S3 VPN Big Pipe SoE) | FS-85:(S3 VPN Big Pipe SoE):{Dynamics - Confirm cmd file changes Successfully Deployed} |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 85:(S3 VPN Big Pipe SoE) | 15.2:(S3 VPN Big Pipe SoE) | 0h 05m | - | 18-04-23 07:35 | 18-04-23 07:40 | EE and D365 | Dynamics - Confirm cmd file changes Successfully Deployed | Dynamics - Confirm cmd file changes Successfully Deployed in folder /SSISPackages/Command MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-84:(S3 VPN Big Pipe SoE) | FS-84:(S3 VPN Big Pipe SoE):[Dynamics - Copy cmd files to Production] | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 86:(S3 VPN Big Pipe SoE) | 15.3:(S3 VPN Big Pipe SoE) | 0h 00m | - | 18-04-23 07:40 | 18-04-23 07:40 |  | cmd file Deployments - Tuesday 07:30 |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 87:(S3 VPN Big Pipe SoE) | 16.0:(S3 VPN Big Pipe SoE) | 8h 25m | - | 18-04-23 09:05 | 18-04-23 17:30 |  | Monitoring - Group 3 Tuesday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 88:(S3 VPN Big Pipe SoE) | 16.1:(S3 VPN Big Pipe SoE) | 8h 00m | 18-04-23 09:05 | 18-04-23 09:05 | 18-04-23 17:05 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 This is to confirm that MasterDataLoad.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 89:(S3 VPN Big Pipe SoE) | 16.2:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 16:00 | 18-04-23 16:00 | 18-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 This is to confirm that IntegrationInstruction_DHRingfenced.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 90:(S3 VPN Big Pipe SoE) | 16.3:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 16:00 | 18-04-23 16:00 | 18-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 This is to confirm that IntegrationInstruction_BOTClosureRetail.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 91:(S3 VPN Big Pipe SoE) | 16.4:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 16:00 | 18-04-23 16:00 | 18-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 This is to confirm that IntegrationInstruction_BOTClosureCommercial.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 92:(S3 VPN Big Pipe SoE) | 16.5:(S3 VPN Big Pipe SoE) | 0h 30m | 18-04-23 17:00 | 18-04-23 17:00 | 18-04-23 17:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 This is to confirm that GoneAway_Case_Closed_D365_to_DH.cmd has been updated correctly. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 93:(S3 VPN Big Pipe SoE) | 16.6:(S3 VPN Big Pipe SoE) | 0h 00m | - | 18-04-23 17:30 | 18-04-23 17:30 |  | Monitoring - Group 3 Tuesday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 94:(S3 VPN Big Pipe SoE) | 17.0:(S3 VPN Big Pipe SoE) | 0h 30m | - | 19-04-23 08:00 | 19-04-23 08:30 |  | Monitoring - Group 3 Wednesday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 95:(S3 VPN Big Pipe SoE) | 17.1:(S3 VPN Big Pipe SoE) | 0h 30m | 19-04-23 08:00 | 19-04-23 08:00 | 19-04-23 08:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 This is to confirm that DH_AccountRingfenced.cmd has been updated correctly. Job ran 19:00 Tuesday evening. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 96:(S3 VPN Big Pipe SoE) | 17.2:(S3 VPN Big Pipe SoE) | 0h 30m | 19-04-23 08:00 | 19-04-23 08:00 | 19-04-23 08:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 This is to confirm that CommunicationCycles.cmd has been updated correctly. Job ran 22:00 Tuesday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 97:(S3 VPN Big Pipe SoE) | 17.3:(S3 VPN Big Pipe SoE) | 0h 00m | - | 19-04-23 08:30 | 19-04-23 08:30 |  | Monitoring - Group 3 Wednesday |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 98:(S3 VPN Big Pipe SoE) | 18.0:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 |  | Implementation Stand-down |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 99:(S3 VPN Big Pipe SoE) | 18.1:(S3 VPN Big Pipe SoE) | 0h 00m | - | 19-04-23 08:30 | 19-04-23 08:30 | Implementation Manager | Milestone - Implementation Complete |  |  | Y | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 100:(S3 VPN Big Pipe SoE) | 18.2:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 | Implementation Manager | Confirm Final Go Decision |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 101:(S3 VPN Big Pipe SoE) | 18.3:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 | Implementation Manager | Send Comms - Implementation Successfully Completed |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 102:(S3 VPN Big Pipe SoE) | 18.4:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 | Implementation Manager | Inform SysOps that change has completed if necessary | Inform SysOps that change has completed if necessary Use email sent for start of change to inform sysops we are complete |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 103:(S3 VPN Big Pipe SoE) | 18.5:(S3 VPN Big Pipe SoE) | 0h 00m | - | 19-04-23 08:45 | 19-04-23 08:45 |  | Implementation Stand-down |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Stage | 104:(S3 VPN Big Pipe SoE) | 19.0:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 |  | Post Implementation Tidy Up |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 105:(S3 VPN Big Pipe SoE) | 19.1:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 | Implementation Manager | Gather Dynamics Checkout Evidence for MCR | Gather Testing evidence and attached to Change record |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 106:(S3 VPN Big Pipe SoE) | 19.2:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 | EE Team | Close Dynamics TCR |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Task | 107:(S3 VPN Big Pipe SoE) | 19.3:(S3 VPN Big Pipe SoE) | 0h 15m | - | 19-04-23 08:30 | 19-04-23 08:45 | Implementation Manager | Close MCR | Gather testing evidence and attach to MCR |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045
Checkpoint | 108:(S3 VPN Big Pipe SoE) | 19.4:(S3 VPN Big Pipe SoE) | 0h 00m | - | 19-04-23 08:45 | 19-04-23 08:45 |  | Post Implementation Tidy Up |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe SoE | 466045

## All Bo (hidden)
ID | Task Type | Phase | ID | Predecessors | Successors | Duration | Start Time | End Time | Explicit Start Time | Title | Owner | Team | Description | Technical Detail | Notes | SoE Name | SoE Number | Skipped | User Def 1 | User Def 2 | User Def 3 | User Def 4 | State | Evt ID | Event Crit Path | ID | Predecessors | Successors | User Def 5 | User Def 6
1.0:(S3 VPN Big Pipe BO) | Stage | Imp | 1.0 | None | None | 1h 00m | 17-04-23 11:30 | 17-04-23 12:30 | - | Prepare for Backout | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 109 | N | 1.0:(466046) | None | None
1.1:(S3 VPN Big Pipe BO) | Task | Imp | 1.1 | None | FS-1.3:(S3 VPN Big Pipe BO), FS-1.4:(S3 VPN Big Pipe BO), FS-1.5:(S3 VPN Big Pipe BO), FS-1.2:(S3 VPN Big Pipe BO) | 0h 00m | 17-04-23 11:30 | 17-04-23 11:30 | 17-04-23 11:30 | Internal Checkpoint - Start Backout of Changes |  | Implementation Manager | Before starting the backout consider if it can be delayed until after the business day has completed. | Shape:Exclude=Y |  | S3 VPN Big Pipe BO | 466046 | Y |  |  |  |  | Review | 110 | N | 1.1:(466046) | None | FS-1.3:(466046), FS-1.4:(466046), FS-1.5:(466046), FS-1.2:(466046)
1.2:(S3 VPN Big Pipe BO) | Task | Imp | 1.2 | FS-1.1:(S3 VPN Big Pipe BO) | None | 0h 10m | 17-04-23 11:30 | 17-04-23 11:40 | - | Inform Sysops and all Stakeholders about implementation backout |  | Implementation Manager | Inform Sysops & Stakeholders about implementation backout is about to commence Send mail to ~ System Operations Mainframe <system.operations@rbs.co.uk> ~ System Operations Offhost <fpitopm@rbs.co.uk> Sys Ops Mainframe : +44 131 626 6510 Sys Ops Off-Host: +44 131 626 6540 Send Email notification to all Stakeholders, sysops, Project team and Business about implementation backout |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 111 | N | 1.2:(466046) | FS-1.1:(466046) | None
1.3:(S3 VPN Big Pipe BO) | Task | Imp | 1.3 | FS-1.1:(S3 VPN Big Pipe BO) | None | 0h 30m | 17-04-23 11:30 | 17-04-23 12:00 | - | Inform Recovery Manager on backout |  | Implementation Manager | Inform Recovery manager on backout Incident & Recovery Management (IRM) team can be reached 24/7 on 0845 300 4829 (International +44 (0)131 549 8300) or #IncidentRecoveryManagement@rbos.co.uk |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 112 | N | 1.3:(466046) | FS-1.1:(466046) | None
1.4:(S3 VPN Big Pipe BO) | Task | Imp | 1.4 | FS-1.1:(S3 VPN Big Pipe BO) | None | 0h 05m | 17-04-23 11:30 | 17-04-23 11:35 | - | Send COMMs to Stakeholders that Backout has been initiated |  | Event Manager |  |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 113 | N | 1.4:(466046) | FS-1.1:(466046) | None
1.5:(S3 VPN Big Pipe BO) | Task | Imp | 1.5 | FS-1.1:(S3 VPN Big Pipe BO) | None | 1h 00m | 17-04-23 11:30 | 17-04-23 12:30 | - | Confirm Backout Requirements |  | Event Manager | Confirm scope of the backout, this is a group of unrelated fixes that are being applied. They can be backed out individually, but be careful to consider and overlapping code that may influence what needs to be backed out. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 114 | N | 1.5:(466046) | FS-1.1:(466046) | None
1.6:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 1.6 | None | None | 0h 00m | 17-04-23 12:30 | 17-04-23 12:30 | - | Prepare for Backout | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 115 | N | 1.6:(466046) | None | None
2.0:(S3 VPN Big Pipe BO) | Stage | Imp | 2.0 | None | None | 0h 35m | 17-04-23 12:00 | 17-04-23 12:35 | - | Backout Dynamics cmd files Changes - First Group |  |  |  | Shape:Colour=255,255,143 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 116 | N | 2.0:(466046) | None | None
2.1:(S3 VPN Big Pipe BO) | Task | Imp | 2.1 | None | FS-2.2:(S3 VPN Big Pipe BO) | 0h 10m | 17-04-23 12:00 | 17-04-23 12:10 | 17-04-23 12:00 | Dynamics - Backout SSIS Package and cmd files in First Group |  | EE and D365 | Dynamics - Backout SSIS Package and cmd files in First Group File locations for production files: /SSISPackages/Command /SSISPackages/DTX First Group cmd Files to Backout: IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd First Group SSIS Packages to Backout: IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx Copy Restore Point SSIS Package and cmd files to Production for any amended packages There is no expect outage for performing the backout Each of the SSIS Packages and cmd file changes can be backed out independently |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 117 | N | 2.1:(466046) | None | FS-2.2:(466046)
2.2:(S3 VPN Big Pipe BO) | Task | Imp | 2.2 | FS-2.1:(S3 VPN Big Pipe BO) | FS-2.3:(S3 VPN Big Pipe BO) | 0h 10m | 17-04-23 12:10 | 17-04-23 12:20 | - | Dynamics Technical Check - Confirm SSIS Packages and cmd files Backed Out for First Group |  | EE and D365 | Dynamics Technical Check - Confirm SSIS Packages and cmd files Backed Out for First Group Confirm First Group cmd Files have been Backed out: IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd Confirm First Group cmd Files have been Backed out: IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx Each of the SSIS Package and cmd files changes can be backed out independently Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 118 | N | 2.2:(466046) | FS-2.1:(466046) | FS-2.3:(466046)
2.3:(S3 VPN Big Pipe BO) | Task | Imp | 2.3 | FS-2.2:(S3 VPN Big Pipe BO) | None | 0h 15m | 17-04-23 12:20 | 17-04-23 12:35 | - | Dynamics - Post Backout Tidy and Job Rerun |  | EE and D365 | Dynamics - Post Backout Tidy and Job Rerun In the event of the change being backed out due to jobs failures. Perform any data / file tidy up as required and perform any adhoc jobs runs to recover to a known good position before resuming the normal job schedules. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 119 | N | 2.3:(466046) | FS-2.2:(466046) | None
2.4:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 2.4 | None | None | 0h 00m | 17-04-23 12:35 | 17-04-23 12:35 | - | Backout Dynamics cmd files Changes - First Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 120 | N | 2.4:(466046) | None | None
3.0:(S3 VPN Big Pipe BO) | Stage | Imp | 3.0 | None | None | 4h 00m | 17-04-23 12:30 | 17-04-23 16:30 | - | Enhanced Job Monitoring - First Group |  |  |  | Shape:Colour=255,255,143 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 121 | N | 3.0:(466046) | None | None
3.1:(S3 VPN Big Pipe BO) | Task | Imp | 3.1 | None | None | 4h 00m | 17-04-23 12:30 | 17-04-23 16:30 | 17-04-23 12:30 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 122 | N | 3.1:(466046) | None | None
3.2:(S3 VPN Big Pipe BO) | Task | Imp | 3.2 | None | None | 4h 00m | 17-04-23 12:30 | 17-04-23 16:30 | 17-04-23 12:30 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 CUSTRM-72540 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 123 | N | 3.2:(466046) | None | None
3.3:(S3 VPN Big Pipe BO) | Task | Imp | 3.3 | None | None | 4h 00m | 17-04-23 12:30 | 17-04-23 16:30 | 17-04-23 12:30 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Job runs Daily - MTWTF - Hourly on xx:25 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 124 | N | 3.3:(466046) | None | None
3.4:(S3 VPN Big Pipe BO) | Task | Imp | 3.4 | None | None | 4h 00m | 17-04-23 12:30 | 17-04-23 16:30 | 17-04-23 12:30 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Job runs Daily - MTWTF - Hourly on xx:40 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 125 | N | 3.4:(466046) | None | None
3.5:(S3 VPN Big Pipe BO) | Task | Imp | 3.5 | None | None | 4h 00m | 17-04-23 12:30 | 17-04-23 16:30 | 17-04-23 12:30 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 126 | N | 3.5:(466046) | None | None
3.6:(S3 VPN Big Pipe BO) | Task | Imp | 3.6 | None | None | 4h 00m | 17-04-23 12:30 | 17-04-23 16:30 | 17-04-23 12:30 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.integrationinstructionspinote.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 127 | N | 3.6:(466046) | None | None
3.7:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 3.7 | None | None | 0h 00m | 17-04-23 16:30 | 17-04-23 16:30 | - | Enhanced Job Monitoring - First Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 128 | N | 3.7:(466046) | None | None
4.0:(S3 VPN Big Pipe BO) | Stage | Imp | 4.0 | None | None | 0h 35m | 18-04-23 08:00 | 18-04-23 08:35 | - | Backout Dynamics cmd files Changes - Second Group |  |  |  | Shape:Colour=248,242,0 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 129 | N | 4.0:(466046) | None | None
4.1:(S3 VPN Big Pipe BO) | Task | Imp | 4.1 | None | FS-4.2:(S3 VPN Big Pipe BO) | 0h 10m | 18-04-23 08:00 | 18-04-23 08:10 | 18-04-23 08:00 | Dynamics - Backout cmd files in Second Group |  | EE and D365 | Dynamics - Backout cmd files in Second Group File locations for production files: /SSISPackages/Command First Group cmd Files to Backout: Tranches_D365_to_DH.cmd IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd Copy Restore Point cmd files to Production for any amended packages There is no expect outage for performing the backout Each of the cmd file changes can be backed out independently |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 130 | N | 4.1:(466046) | None | FS-4.2:(466046)
4.2:(S3 VPN Big Pipe BO) | Task | Imp | 4.2 | FS-4.1:(S3 VPN Big Pipe BO) | FS-4.3:(S3 VPN Big Pipe BO) | 0h 10m | 18-04-23 08:10 | 18-04-23 08:20 | - | Dynamics Technical Check - Confirm cmd files Backed Out for Second Group |  | EE and D365 | Dynamics Technical Check - Confirm cmd files Backed Out for Second Group Confirm First Group cmd Files have been Backed out: Tranches_D365_to_DH.cmd IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd Each of the cmd file changes can be backed out independently Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 131 | N | 4.2:(466046) | FS-4.1:(466046) | FS-4.3:(466046)
4.3:(S3 VPN Big Pipe BO) | Task | Imp | 4.3 | FS-4.2:(S3 VPN Big Pipe BO) | None | 0h 15m | 18-04-23 08:20 | 18-04-23 08:35 | - | Dynamics - Post Backout Tidy and Job Rerun |  | EE and D365 | Dynamics - Post Backout Tidy and Job Rerun In the event of the change being backed out due to jobs failures. Perform any data / file tidy up as required and perform any adhoc jobs runs to recover to a known good position before resuming the normal job schedules. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 132 | N | 4.3:(466046) | FS-4.2:(466046) | None
4.4:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 4.4 | None | None | 0h 00m | 18-04-23 08:35 | 18-04-23 08:35 | - | Backout Dynamics cmd files Changes - Second Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 133 | N | 4.4:(466046) | None | None
5.0:(S3 VPN Big Pipe BO) | Stage | Imp | 5.0 | None | None | 8h 00m | 18-04-23 12:55 | 18-04-23 20:55 | - | Enhanced Job Monitoring - Second Group |  |  |  | Shape:Colour=248,242,0 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 134 | N | 5.0:(466046) | None | None
5.1:(S3 VPN Big Pipe BO) | Task | Imp | 5.1 | None | None | 8h 00m | 18-04-23 12:55 | 18-04-23 20:55 | 18-04-23 12:55 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 This jobs runs hourly on 15 mins passed the hour. Keep monitoring this job until is is confirmed that job has processed data. This is a possibility that the job may not get any data to process on Monday, if this is the case continue monitoring on Tuesday as required. If we are struggling to confirm the job check with Dynamics and the Event Manager when to stop monitoring. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 135 | N | 5.1:(466046) | None | None
5.2:(S3 VPN Big Pipe BO) | Task | Imp | 5.2 | None | None | 0h 30m | 18-04-23 14:00 | 18-04-23 14:30 | 18-04-23 14:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 136 | N | 5.2:(466046) | None | None
5.3:(S3 VPN Big Pipe BO) | Task | Imp | 5.3 | None | None | 0h 30m | 18-04-23 17:00 | 18-04-23 17:30 | 18-04-23 17:00 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 137 | N | 5.3:(466046) | None | None
5.4:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 5.4 | None | None | 0h 00m | 18-04-23 20:55 | 18-04-23 20:55 | - | Enhanced Job Monitoring - Second Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 138 | N | 5.4:(466046) | None | None
6.0:(S3 VPN Big Pipe BO) | Stage | Imp | 6.0 | None | None | 4h 00m | 19-04-23 06:00 | 19-04-23 10:00 | - | Enhanced Job Monitoring - Second Group |  |  |  | Shape:Colour=248,242,0 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 139 | N | 6.0:(466046) | None | None
6.1:(S3 VPN Big Pipe BO) | Task | Imp | 6.1 | None | None | 0h 30m | 19-04-23 06:00 | 19-04-23 06:30 | 19-04-23 06:00 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 Job ran @ 23:00 Monday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 140 | N | 6.1:(466046) | None | None
6.2:(S3 VPN Big Pipe BO) | Task | Imp | 6.2 | None | None | 0h 30m | 19-04-23 06:00 | 19-04-23 06:30 | 19-04-23 06:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 141 | N | 6.2:(466046) | None | None
6.3:(S3 VPN Big Pipe BO) | Task | Imp | 6.3 | None | None | 0h 30m | 19-04-23 07:45 | 19-04-23 08:15 | 19-04-23 07:45 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 142 | N | 6.3:(466046) | None | None
6.4:(S3 VPN Big Pipe BO) | Task | Imp | 6.4 | None | None | 0h 30m | 19-04-23 08:00 | 19-04-23 08:30 | 19-04-23 08:00 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 143 | N | 6.4:(466046) | None | None
6.5:(S3 VPN Big Pipe BO) | Task | Imp | 6.5 | None | None | 0h 30m | 19-04-23 08:30 | 19-04-23 09:00 | 19-04-23 08:30 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 144 | N | 6.5:(466046) | None | None
6.6:(S3 VPN Big Pipe BO) | Task | Imp | 6.6 | None | None | 0h 30m | 19-04-23 09:00 | 19-04-23 09:30 | 19-04-23 09:00 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 145 | N | 6.6:(466046) | None | None
6.7:(S3 VPN Big Pipe BO) | Task | Imp | 6.7 | None | None | 0h 30m | 19-04-23 09:30 | 19-04-23 10:00 | 19-04-23 09:30 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 146 | N | 6.7:(466046) | None | None
6.8:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 6.8 | None | None | 0h 00m | 19-04-23 10:00 | 19-04-23 10:00 | - | Enhanced Job Monitoring - Second Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 147 | N | 6.8:(466046) | None | None
7.0:(S3 VPN Big Pipe BO) | Stage | Imp | 7.0 | None | None | 0h 35m | 19-04-23 08:00 | 19-04-23 08:35 | - | Backout Dynamics cmd files Changes - Third Group |  |  |  | Shape:Colour=149,146,0 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 148 | N | 7.0:(466046) | None | None
7.1:(S3 VPN Big Pipe BO) | Task | Imp | 7.1 | None | FS-7.2:(S3 VPN Big Pipe BO) | 0h 10m | 19-04-23 08:00 | 19-04-23 08:10 | 19-04-23 08:00 | Dynamics - Backout cmd files in Third Group |  | EE and D365 | Dynamics - Backout cmd files in Third Group File locations for production files: /SSISPackages/Command First Group cmd Files to Backout: MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd Copy Restore Point cmd files to Production for any amended packages There is no expect outage for performing the backout Each of the cmd files changes can be backed out independently |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 149 | N | 7.1:(466046) | None | FS-7.2:(466046)
7.2:(S3 VPN Big Pipe BO) | Task | Imp | 7.2 | FS-7.1:(S3 VPN Big Pipe BO) | FS-7.3:(S3 VPN Big Pipe BO) | 0h 10m | 19-04-23 08:10 | 19-04-23 08:20 | - | Dynamics Technical Check - Confirm cmd files Backed Out for Third Group |  | EE and D365 | Dynamics Technical Check - Confirm cmd files Backed Out for Third Group Confirm First Group cmd Files have been Backed out: MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd Each of the cmd files changes can be backed out independently Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 150 | N | 7.2:(466046) | FS-7.1:(466046) | FS-7.3:(466046)
7.3:(S3 VPN Big Pipe BO) | Task | Imp | 7.3 | FS-7.2:(S3 VPN Big Pipe BO) | None | 0h 15m | 19-04-23 08:20 | 19-04-23 08:35 | - | Dynamics - Post Backout Tidy and Job Rerun |  | EE and D365 | Dynamics - Post Backout Tidy and Job Rerun In the event of the change being backed out due to jobs failures. Perform any data / file tidy up as required and perform any adhoc jobs runs to recover to a known good position before resuming the normal job schedules. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 151 | N | 7.3:(466046) | FS-7.2:(466046) | None
7.4:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 7.4 | None | None | 0h 00m | 19-04-23 08:35 | 19-04-23 08:35 | - | Backout Dynamics cmd files Changes - Third Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 152 | N | 7.4:(466046) | None | None
8.0:(S3 VPN Big Pipe BO) | Stage | Imp | 8.0 | None | None | 8h 25m | 19-04-23 09:05 | 19-04-23 17:30 | - | Enhanced Job Monitoring - Third Group |  |  |  | Shape:Colour=149,146,0 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 153 | N | 8.0:(466046) | None | None
8.1:(S3 VPN Big Pipe BO) | Task | Imp | 8.1 | None | None | 8h 00m | 19-04-23 09:05 | 19-04-23 17:05 | 19-04-23 09:05 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 154 | N | 8.1:(466046) | None | None
8.2:(S3 VPN Big Pipe BO) | Task | Imp | 8.2 | None | None | 0h 30m | 19-04-23 16:00 | 19-04-23 16:30 | 19-04-23 16:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 155 | N | 8.2:(466046) | None | None
8.3:(S3 VPN Big Pipe BO) | Task | Imp | 8.3 | None | None | 0h 30m | 19-04-23 16:00 | 19-04-23 16:30 | 19-04-23 16:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 156 | N | 8.3:(466046) | None | None
8.4:(S3 VPN Big Pipe BO) | Task | Imp | 8.4 | None | None | 0h 30m | 19-04-23 16:00 | 19-04-23 16:30 | 19-04-23 16:00 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 157 | N | 8.4:(466046) | None | None
8.5:(S3 VPN Big Pipe BO) | Task | Imp | 8.5 | None | None | 0h 30m | 19-04-23 17:00 | 19-04-23 17:30 | 19-04-23 17:00 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 158 | N | 8.5:(466046) | None | None
8.6:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 8.6 | None | None | 0h 00m | 19-04-23 17:30 | 19-04-23 17:30 | - | Enhanced Job Monitoring - Third Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 159 | N | 8.6:(466046) | None | None
9.0:(S3 VPN Big Pipe BO) | Stage | Imp | 9.0 | None | None | 0h 30m | 20-04-23 08:00 | 20-04-23 08:30 | - | Enhanced Job Monitoring - Third Group |  |  |  | Shape:Colour=149,146,0 |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 160 | Y | 9.0:(466046) | None | None
9.1:(S3 VPN Big Pipe BO) | Task | Imp | 9.1 | None | None | 0h 30m | 20-04-23 08:00 | 20-04-23 08:30 | 20-04-23 08:00 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 Job ran 19:00 Tuesday evening. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 161 | Y | 9.1:(466046) | None | None
9.2:(S3 VPN Big Pipe BO) | Task | Imp | 9.2 | None | None | 0h 30m | 20-04-23 08:00 | 20-04-23 08:30 | 20-04-23 08:00 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 |  | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 Job ran 22:00 Tuesday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 162 | Y | 9.2:(466046) | None | None
9.3:(S3 VPN Big Pipe BO) | Checkpoint | Imp | 9.3 | None | None | 0h 00m | 20-04-23 08:30 | 20-04-23 08:30 | - | Enhanced Job Monitoring - Third Group | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 163 | Y | 9.3:(466046) | None | None
10.0:(S3 VPN Big Pipe BO) | Stage | Post | 10.0 | None | None | 0h 05m | 20-04-23 08:30 | 20-04-23 08:35 | - | Backout Closedown | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 164 | N | 10.0:(466046) | None | None
10.1:(S3 VPN Big Pipe BO) | Task | Post | 10.1 | None | None | 0h 00m | 20-04-23 08:30 | 20-04-23 08:30 | - | Internal Checkpoint - Backout of Changes Successfully Completed |  | Implementation Manager |  |  |  | S3 VPN Big Pipe BO | 466046 | Y |  |  |  |  | Review | 165 | N | 10.1:(466046) | None | None
10.2:(S3 VPN Big Pipe BO) | Task | Post | 10.2 | None | None | 0h 05m | 20-04-23 08:30 | 20-04-23 08:35 | - | Inform Sysops that Backout has completed |  | Implementation Manager |  |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 166 | N | 10.2:(466046) | None | None
10.3:(S3 VPN Big Pipe BO) | Task | Post | 10.3 | None | None | 0h 05m | 20-04-23 08:30 | 20-04-23 08:35 | - | Close Command and Control Line |  | Implementation Manager |  |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 167 | N | 10.3:(466046) | None | None
10.4:(S3 VPN Big Pipe BO) | Task | Post | 10.4 | None | None | 0h 05m | 20-04-23 08:30 | 20-04-23 08:35 | - | Send COMMs to Stakeholders that Backout has completed |  | Event Manager |  |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 168 | N | 10.4:(466046) | None | None
10.5:(S3 VPN Big Pipe BO) | Checkpoint | Post | 10.5 | None | None | 0h 00m | 20-04-23 08:35 | 20-04-23 08:35 | - | Backout Closedown | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 169 | N | 10.5:(466046) | None | None
11.0:(S3 VPN Big Pipe BO) | Stage | Post | 11.0 | None | None | 1h 00m | 20-04-23 08:30 | 20-04-23 09:30 | - | Post Backout Tidy Up | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Pre-Activated | 170 | N | 11.0:(466046) | None | None
11.1:(S3 VPN Big Pipe BO) | Task | Post | 11.1 | None | None | 1h 00m | 20-04-23 08:30 | 20-04-23 09:30 | - | Close Dynamics TCR for Implementation |  | EE Team |  |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 171 | N | 11.1:(466046) | None | None
11.2:(S3 VPN Big Pipe BO) | Task | Post | 11.2 | None | None | 1h 00m | 20-04-23 08:30 | 20-04-23 09:30 | - | Gather Testing Results for Dynamics |  | Implementation Manager | Gather Testing evidence and attached to Change record |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 172 | N | 11.2:(466046) | None | None
11.3:(S3 VPN Big Pipe BO) | Task | Post | 11.3 | None | None | 1h 00m | 20-04-23 08:30 | 20-04-23 09:30 | - | Close MCR for Implementation |  | Implementation Manager | Answer following question in MCR: Attach Gathered Testing Evidence 17. Update this section with the relevant details pertaining to the issue which occurred during or post change. Below are the questions that need to be answered. 17a. What was the root cause of the issue? 17b. What was done to remediate the issue? 17c. What will be done to ensure this does not happen in the future again? |  |  | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 173 | N | 11.3:(466046) | None | None
11.4:(S3 VPN Big Pipe BO) | Checkpoint | Post | 11.4 | None | None | 0h 00m | 20-04-23 09:30 | 20-04-23 09:30 | - | Post Backout Tidy Up | [5 empty] | S3 VPN Big Pipe BO | 466046 | N |  |  |  |  | Review | 174 | N | 11.4:(466046) | None | None

## Event Backout
Task Identifier |  |  | Timings |  |  |  |  | Task Information | [7 empty] | Filters |  |  |  | ICEFLO SoE Information
Task Type | Event Task Id (EVT ID) | SoE Id (ID) | Duration | Expicit Start Time | Start Time | End Time | Team | Title | Description | Tech Detail | Skip | Predecessors (EVT Id) | Predecessors Expanded | Successors (EVT Id) | Successors Expanded | User Defined 1 | User Defined 2 | User Defined 3 | User Defined 4 | SoE Name | SoE Number
Stage | 109:(S3 VPN Big Pipe BO) | 1.0:(S3 VPN Big Pipe BO) | 1h 00m | - | 17-04-23 11:30 | 17-04-23 12:30 |  | Prepare for Backout |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 110:(S3 VPN Big Pipe BO) | 1.1:(S3 VPN Big Pipe BO) | 0h 00m | 17-04-23 11:30 | 17-04-23 11:30 | 17-04-23 11:30 | Implementation Manager | Internal Checkpoint - Start Backout of Changes | Before starting the backout consider if it can be delayed until after the business day has completed. |  | Y | None | None | FS-112:(S3 VPN Big Pipe BO), FS-113:(S3 VPN Big Pipe BO), FS-114:(S3 VPN Big Pipe BO), FS-111:(S3 VPN Big Pipe BO) | FS-112:(S3 VPN Big Pipe BO):{Inform Recovery Manager on backout}, FS-113:(S3 VPN Big Pipe BO):{Send COMMs to Stakeholders that Backout has been initiated}, FS-114:(S3 VPN Big Pipe BO):{Confirm Backout Requirements}, FS-111:(S3 VPN Big Pipe BO):{Inform Sysops and all Stakeholders about implementation backout} |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 111:(S3 VPN Big Pipe BO) | 1.2:(S3 VPN Big Pipe BO) | 0h 10m | - | 17-04-23 11:30 | 17-04-23 11:40 | Implementation Manager | Inform Sysops and all Stakeholders about implementation backout | Inform Sysops & Stakeholders about implementation backout is about to commence Send mail to ~ System Operations Mainframe <system.operations@rbs.co.uk> ~ System Operations Offhost <fpitopm@rbs.co.uk> Sys Ops Mainframe : +44 131 626 6510 Sys Ops Off-Host: +44 131 626 6540 Send Email notification to all Stakeholders, sysops, Project team and Business about implementation backout |  | N | FS-110:(S3 VPN Big Pipe BO) | FS-110:(S3 VPN Big Pipe BO):[Internal Checkpoint - Start Backout of Changes] | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 112:(S3 VPN Big Pipe BO) | 1.3:(S3 VPN Big Pipe BO) | 0h 30m | - | 17-04-23 11:30 | 17-04-23 12:00 | Implementation Manager | Inform Recovery Manager on backout | Inform Recovery manager on backout Incident & Recovery Management (IRM) team can be reached 24/7 on 0845 300 4829 (International +44 (0)131 549 8300) or #IncidentRecoveryManagement@rbos.co.uk |  | N | FS-110:(S3 VPN Big Pipe BO) | FS-110:(S3 VPN Big Pipe BO):[Internal Checkpoint - Start Backout of Changes] | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 113:(S3 VPN Big Pipe BO) | 1.4:(S3 VPN Big Pipe BO) | 0h 05m | - | 17-04-23 11:30 | 17-04-23 11:35 | Event Manager | Send COMMs to Stakeholders that Backout has been initiated |  |  | N | FS-110:(S3 VPN Big Pipe BO) | FS-110:(S3 VPN Big Pipe BO):[Internal Checkpoint - Start Backout of Changes] | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 114:(S3 VPN Big Pipe BO) | 1.5:(S3 VPN Big Pipe BO) | 1h 00m | - | 17-04-23 11:30 | 17-04-23 12:30 | Event Manager | Confirm Backout Requirements | Confirm scope of the backout, this is a group of unrelated fixes that are being applied. They can be backed out individually, but be careful to consider and overlapping code that may influence what needs to be backed out. |  | N | FS-110:(S3 VPN Big Pipe BO) | FS-110:(S3 VPN Big Pipe BO):[Internal Checkpoint - Start Backout of Changes] | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 115:(S3 VPN Big Pipe BO) | 1.6:(S3 VPN Big Pipe BO) | 0h 00m | - | 17-04-23 12:30 | 17-04-23 12:30 |  | Prepare for Backout |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 116:(S3 VPN Big Pipe BO) | 2.0:(S3 VPN Big Pipe BO) | 0h 35m | - | 17-04-23 12:00 | 17-04-23 12:35 |  | Backout Dynamics cmd files Changes - First Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 117:(S3 VPN Big Pipe BO) | 2.1:(S3 VPN Big Pipe BO) | 0h 10m | 17-04-23 12:00 | 17-04-23 12:00 | 17-04-23 12:10 | EE and D365 | Dynamics - Backout SSIS Package and cmd files in First Group | Dynamics - Backout SSIS Package and cmd files in First Group File locations for production files: /SSISPackages/Command /SSISPackages/DTX First Group cmd Files to Backout: IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd First Group SSIS Packages to Backout: IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx Copy Restore Point SSIS Package and cmd files to Production for any amended packages There is no expect outage for performing the backout Each of the SSIS Packages and cmd file changes can be backed out independently |  | N | None | None | FS-118:(S3 VPN Big Pipe BO) | FS-118:(S3 VPN Big Pipe BO):{Dynamics Technical Check - Confirm SSIS Packages and cmd files Backed Out for First Group} |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 118:(S3 VPN Big Pipe BO) | 2.2:(S3 VPN Big Pipe BO) | 0h 10m | - | 17-04-23 12:10 | 17-04-23 12:20 | EE and D365 | Dynamics Technical Check - Confirm SSIS Packages and cmd files Backed Out for First Group | Dynamics Technical Check - Confirm SSIS Packages and cmd files Backed Out for First Group Confirm First Group cmd Files have been Backed out: IntegrationInstruction_TrancheUpdateFacility.cmd IntegrationInstruction_CohortTrancheUpdate.cmd IntegrationInstruction_SPINote.cmd IntegrationInstruction_CommercialClosureBOT.cmd Confirm First Group cmd Files have been Backed out: IntegrationInstruction_CommercialClosureBOT.dtsx IntegrationInstruction_TrancheUpdateFacility.dtsx Each of the SSIS Package and cmd files changes can be backed out independently Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-117:(S3 VPN Big Pipe BO) | FS-117:(S3 VPN Big Pipe BO):[Dynamics - Backout SSIS Package and cmd files in First Group] | FS-119:(S3 VPN Big Pipe BO) | FS-119:(S3 VPN Big Pipe BO):{Dynamics - Post Backout Tidy and Job Rerun} |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 119:(S3 VPN Big Pipe BO) | 2.3:(S3 VPN Big Pipe BO) | 0h 15m | - | 17-04-23 12:20 | 17-04-23 12:35 | EE and D365 | Dynamics - Post Backout Tidy and Job Rerun | Dynamics - Post Backout Tidy and Job Rerun In the event of the change being backed out due to jobs failures. Perform any data / file tidy up as required and perform any adhoc jobs runs to recover to a known good position before resuming the normal job schedules. |  | N | FS-118:(S3 VPN Big Pipe BO) | FS-118:(S3 VPN Big Pipe BO):[Dynamics Technical Check - Confirm SSIS Packages and cmd files Backed Out for First Group] | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 120:(S3 VPN Big Pipe BO) | 2.4:(S3 VPN Big Pipe BO) | 0h 00m | - | 17-04-23 12:35 | 17-04-23 12:35 |  | Backout Dynamics cmd files Changes - First Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 121:(S3 VPN Big Pipe BO) | 3.0:(S3 VPN Big Pipe BO) | 4h 00m | - | 17-04-23 12:30 | 17-04-23 16:30 |  | Enhanced Job Monitoring - First Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 122:(S3 VPN Big Pipe BO) | 3.1:(S3 VPN Big Pipe BO) | 4h 00m | 17-04-23 12:30 | 17-04-23 12:30 | 17-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 123:(S3 VPN Big Pipe BO) | 3.2:(S3 VPN Big Pipe BO) | 4h 00m | 17-04-23 12:30 | 17-04-23 12:30 | 17-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncohorttranchestatusupdate.ep1 CUSTRM-72540 Job runs Daily - MTWTF - Hourly on xx:10 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.intinstructioncohorttrancheupdate.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 124:(S3 VPN Big Pipe BO) | 3.3:(S3 VPN Big Pipe BO) | 4h 00m | 17-04-23 12:30 | 17-04-23 12:30 | 17-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructioncommercialclosurebot.ep1 Job runs Daily - MTWTF - Hourly on xx:25 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 125:(S3 VPN Big Pipe BO) | 3.4:(S3 VPN Big Pipe BO) | 4h 00m | 17-04-23 12:30 | 17-04-23 12:30 | 17-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.intinstructiontrancheupdatefacility.ep1 Job runs Daily - MTWTF - Hourly on xx:40 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 126:(S3 VPN Big Pipe BO) | 3.5:(S3 VPN Big Pipe BO) | 4h 00m | 17-04-23 12:30 | 17-04-23 12:30 | 17-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinote.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 127:(S3 VPN Big Pipe BO) | 3.6:(S3 VPN Big Pipe BO) | 4h 00m | 17-04-23 12:30 | 17-04-23 12:30 | 17-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionspinotestatusupdate.ep1 Job runs Daily - MTWTF - Hourly on xx:55 - 00:00 to 23:59 and is dependent on msd.edi.prd.wdl.integrationinstructionspinote.ep1 completing successfully Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 128:(S3 VPN Big Pipe BO) | 3.7:(S3 VPN Big Pipe BO) | 0h 00m | - | 17-04-23 16:30 | 17-04-23 16:30 |  | Enhanced Job Monitoring - First Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 129:(S3 VPN Big Pipe BO) | 4.0:(S3 VPN Big Pipe BO) | 0h 35m | - | 18-04-23 08:00 | 18-04-23 08:35 |  | Backout Dynamics cmd files Changes - Second Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 130:(S3 VPN Big Pipe BO) | 4.1:(S3 VPN Big Pipe BO) | 0h 10m | 18-04-23 08:00 | 18-04-23 08:00 | 18-04-23 08:10 | EE and D365 | Dynamics - Backout cmd files in Second Group | Dynamics - Backout cmd files in Second Group File locations for production files: /SSISPackages/Command First Group cmd Files to Backout: Tranches_D365_to_DH.cmd IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd Copy Restore Point cmd files to Production for any amended packages There is no expect outage for performing the backout Each of the cmd file changes can be backed out independently |  | N | None | None | FS-131:(S3 VPN Big Pipe BO) | FS-131:(S3 VPN Big Pipe BO):{Dynamics Technical Check - Confirm cmd files Backed Out for Second Group} |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 131:(S3 VPN Big Pipe BO) | 4.2:(S3 VPN Big Pipe BO) | 0h 10m | - | 18-04-23 08:10 | 18-04-23 08:20 | EE and D365 | Dynamics Technical Check - Confirm cmd files Backed Out for Second Group | Dynamics Technical Check - Confirm cmd files Backed Out for Second Group Confirm First Group cmd Files have been Backed out: Tranches_D365_to_DH.cmd IntegrationInstructionsR3_CoreCharges.cmd SwitcherBOT_Commercial_D365_to_DH.cmd ForceClosureException_CoreCharges.cmd IntegrationInstruction_DHReporting.cmd ForceClosureException_CoreAccounting.cmd OverDraftLimit_SendIntegrationInstructions.cmd IntegrationInstruction_IncludeInClosureLetter4.cmd OverDraftLimit_CaptureFeedback_DH_D365.cmd IntegrationInstructionsR3_CoreAccounting.cmd Each of the cmd file changes can be backed out independently Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-130:(S3 VPN Big Pipe BO) | FS-130:(S3 VPN Big Pipe BO):[Dynamics - Backout cmd files in Second Group] | FS-132:(S3 VPN Big Pipe BO) | FS-132:(S3 VPN Big Pipe BO):{Dynamics - Post Backout Tidy and Job Rerun} |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 132:(S3 VPN Big Pipe BO) | 4.3:(S3 VPN Big Pipe BO) | 0h 15m | - | 18-04-23 08:20 | 18-04-23 08:35 | EE and D365 | Dynamics - Post Backout Tidy and Job Rerun | Dynamics - Post Backout Tidy and Job Rerun In the event of the change being backed out due to jobs failures. Perform any data / file tidy up as required and perform any adhoc jobs runs to recover to a known good position before resuming the normal job schedules. |  | N | FS-131:(S3 VPN Big Pipe BO) | FS-131:(S3 VPN Big Pipe BO):[Dynamics Technical Check - Confirm cmd files Backed Out for Second Group] | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 133:(S3 VPN Big Pipe BO) | 4.4:(S3 VPN Big Pipe BO) | 0h 00m | - | 18-04-23 08:35 | 18-04-23 08:35 |  | Backout Dynamics cmd files Changes - Second Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 134:(S3 VPN Big Pipe BO) | 5.0:(S3 VPN Big Pipe BO) | 8h 00m | - | 18-04-23 12:55 | 18-04-23 20:55 |  | Enhanced Job Monitoring - Second Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 135:(S3 VPN Big Pipe BO) | 5.1:(S3 VPN Big Pipe BO) | 8h 00m | 18-04-23 12:55 | 18-04-23 12:55 | 18-04-23 20:55 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.tranchesd365todh.ep1 This jobs runs hourly on 15 mins passed the hour. Keep monitoring this job until is is confirmed that job has processed data. This is a possibility that the job may not get any data to process on Monday, if this is the case continue monitoring on Tuesday as required. If we are struggling to confirm the job check with Dynamics and the Event Manager when to stop monitoring. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 136:(S3 VPN Big Pipe BO) | 5.2:(S3 VPN Big Pipe BO) | 0h 30m | 18-04-23 14:00 | 18-04-23 14:00 | 18-04-23 14:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3corecharges.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 137:(S3 VPN Big Pipe BO) | 5.3:(S3 VPN Big Pipe BO) | 0h 30m | 18-04-23 17:00 | 18-04-23 17:00 | 18-04-23 17:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.switcherbotcommerciald365todh.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 138:(S3 VPN Big Pipe BO) | 5.4:(S3 VPN Big Pipe BO) | 0h 00m | - | 18-04-23 20:55 | 18-04-23 20:55 |  | Enhanced Job Monitoring - Second Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 139:(S3 VPN Big Pipe BO) | 6.0:(S3 VPN Big Pipe BO) | 4h 00m | - | 19-04-23 06:00 | 19-04-23 10:00 |  | Enhanced Job Monitoring - Second Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 140:(S3 VPN Big Pipe BO) | 6.1:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 06:00 | 19-04-23 06:00 | 19-04-23 06:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncorecharges.ep1 Job ran @ 23:00 Monday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 141:(S3 VPN Big Pipe BO) | 6.2:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 06:00 | 19-04-23 06:00 | 19-04-23 06:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhreporting.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 142:(S3 VPN Big Pipe BO) | 6.3:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 07:45 | 19-04-23 07:45 | 19-04-23 08:15 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.forceclosureexceptioncoreaccounting.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 143:(S3 VPN Big Pipe BO) | 6.4:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 08:00 | 19-04-23 08:00 | 19-04-23 08:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitsendintegrationinstruction.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 144:(S3 VPN Big Pipe BO) | 6.5:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 08:30 | 19-04-23 08:30 | 19-04-23 09:00 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionletter4.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 145:(S3 VPN Big Pipe BO) | 6.6:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 09:00 | 19-04-23 09:00 | 19-04-23 09:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.overdraftlimitcapturefeedbackdhd365.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 146:(S3 VPN Big Pipe BO) | 6.7:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 09:30 | 19-04-23 09:30 | 19-04-23 10:00 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionsr3coreaccounting.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 147:(S3 VPN Big Pipe BO) | 6.8:(S3 VPN Big Pipe BO) | 0h 00m | - | 19-04-23 10:00 | 19-04-23 10:00 |  | Enhanced Job Monitoring - Second Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 148:(S3 VPN Big Pipe BO) | 7.0:(S3 VPN Big Pipe BO) | 0h 35m | - | 19-04-23 08:00 | 19-04-23 08:35 |  | Backout Dynamics cmd files Changes - Third Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 149:(S3 VPN Big Pipe BO) | 7.1:(S3 VPN Big Pipe BO) | 0h 10m | 19-04-23 08:00 | 19-04-23 08:00 | 19-04-23 08:10 | EE and D365 | Dynamics - Backout cmd files in Third Group | Dynamics - Backout cmd files in Third Group File locations for production files: /SSISPackages/Command First Group cmd Files to Backout: MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd Copy Restore Point cmd files to Production for any amended packages There is no expect outage for performing the backout Each of the cmd files changes can be backed out independently |  | N | None | None | FS-150:(S3 VPN Big Pipe BO) | FS-150:(S3 VPN Big Pipe BO):{Dynamics Technical Check - Confirm cmd files Backed Out for Third Group} |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 150:(S3 VPN Big Pipe BO) | 7.2:(S3 VPN Big Pipe BO) | 0h 10m | - | 19-04-23 08:10 | 19-04-23 08:20 | EE and D365 | Dynamics Technical Check - Confirm cmd files Backed Out for Third Group | Dynamics Technical Check - Confirm cmd files Backed Out for Third Group Confirm First Group cmd Files have been Backed out: MasterDataLoad.cmd IntegrationInstruction_DHRingfenced.cmd IntegrationInstruction_BOTClosureCommercial.cmd IntegrationInstruction_BOTClosureRetail.cmd GoneAway_Case_Closed_D365_to_DH.cmd DH_AccountRingfenced.cmd CommunicationCycles.cmd Each of the cmd files changes can be backed out independently Record and keep evidence out testing/outcome to be supplied to implementation manager when implementation ends |  | N | FS-149:(S3 VPN Big Pipe BO) | FS-149:(S3 VPN Big Pipe BO):[Dynamics - Backout cmd files in Third Group] | FS-151:(S3 VPN Big Pipe BO) | FS-151:(S3 VPN Big Pipe BO):{Dynamics - Post Backout Tidy and Job Rerun} |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 151:(S3 VPN Big Pipe BO) | 7.3:(S3 VPN Big Pipe BO) | 0h 15m | - | 19-04-23 08:20 | 19-04-23 08:35 | EE and D365 | Dynamics - Post Backout Tidy and Job Rerun | Dynamics - Post Backout Tidy and Job Rerun In the event of the change being backed out due to jobs failures. Perform any data / file tidy up as required and perform any adhoc jobs runs to recover to a known good position before resuming the normal job schedules. |  | N | FS-150:(S3 VPN Big Pipe BO) | FS-150:(S3 VPN Big Pipe BO):[Dynamics Technical Check - Confirm cmd files Backed Out for Third Group] | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 152:(S3 VPN Big Pipe BO) | 7.4:(S3 VPN Big Pipe BO) | 0h 00m | - | 19-04-23 08:35 | 19-04-23 08:35 |  | Backout Dynamics cmd files Changes - Third Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 153:(S3 VPN Big Pipe BO) | 8.0:(S3 VPN Big Pipe BO) | 8h 25m | - | 19-04-23 09:05 | 19-04-23 17:30 |  | Enhanced Job Monitoring - Third Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 154:(S3 VPN Big Pipe BO) | 8.1:(S3 VPN Big Pipe BO) | 8h 00m | 19-04-23 09:05 | 19-04-23 09:05 | 19-04-23 17:05 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.masterdataload.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 155:(S3 VPN Big Pipe BO) | 8.2:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 16:00 | 19-04-23 16:00 | 19-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructiondhringfenced.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 156:(S3 VPN Big Pipe BO) | 8.3:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 16:00 | 19-04-23 16:00 | 19-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosureretail.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 157:(S3 VPN Big Pipe BO) | 8.4:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 16:00 | 19-04-23 16:00 | 19-04-23 16:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.integrationinstructionbotclosurecommercial.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 158:(S3 VPN Big Pipe BO) | 8.5:(S3 VPN Big Pipe BO) | 0h 30m | 19-04-23 17:00 | 19-04-23 17:00 | 19-04-23 17:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.goneawaycaseclosed.ep1 Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 159:(S3 VPN Big Pipe BO) | 8.6:(S3 VPN Big Pipe BO) | 0h 00m | - | 19-04-23 17:30 | 19-04-23 17:30 |  | Enhanced Job Monitoring - Third Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 160:(S3 VPN Big Pipe BO) | 9.0:(S3 VPN Big Pipe BO) | 0h 30m | - | 20-04-23 08:00 | 20-04-23 08:30 |  | Enhanced Job Monitoring - Third Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 161:(S3 VPN Big Pipe BO) | 9.1:(S3 VPN Big Pipe BO) | 0h 30m | 20-04-23 08:00 | 20-04-23 08:00 | 20-04-23 08:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.dhaccountringfenced.ep1 Job ran 19:00 Tuesday evening. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 162:(S3 VPN Big Pipe BO) | 9.2:(S3 VPN Big Pipe BO) | 0h 30m | 20-04-23 08:00 | 20-04-23 08:00 | 20-04-23 08:30 | EE and D365 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 | Dynamics Technical Check - msd.edi.prd.wdl.communicationcycles.ep1 Job ran 22:00 Tuesday night. Confirm Job has completed successfully and produced the expected output. Rerun this job as necessary, perform any data tidy up required to allow job to rerun. |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 163:(S3 VPN Big Pipe BO) | 9.3:(S3 VPN Big Pipe BO) | 0h 00m | - | 20-04-23 08:30 | 20-04-23 08:30 |  | Enhanced Job Monitoring - Third Group |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 164:(S3 VPN Big Pipe BO) | 10.0:(S3 VPN Big Pipe BO) | 0h 05m | - | 20-04-23 08:30 | 20-04-23 08:35 |  | Backout Closedown |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 165:(S3 VPN Big Pipe BO) | 10.1:(S3 VPN Big Pipe BO) | 0h 00m | - | 20-04-23 08:30 | 20-04-23 08:30 | Implementation Manager | Internal Checkpoint - Backout of Changes Successfully Completed |  |  | Y | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 166:(S3 VPN Big Pipe BO) | 10.2:(S3 VPN Big Pipe BO) | 0h 05m | - | 20-04-23 08:30 | 20-04-23 08:35 | Implementation Manager | Inform Sysops that Backout has completed |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 167:(S3 VPN Big Pipe BO) | 10.3:(S3 VPN Big Pipe BO) | 0h 05m | - | 20-04-23 08:30 | 20-04-23 08:35 | Implementation Manager | Close Command and Control Line |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 168:(S3 VPN Big Pipe BO) | 10.4:(S3 VPN Big Pipe BO) | 0h 05m | - | 20-04-23 08:30 | 20-04-23 08:35 | Event Manager | Send COMMs to Stakeholders that Backout has completed |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 169:(S3 VPN Big Pipe BO) | 10.5:(S3 VPN Big Pipe BO) | 0h 00m | - | 20-04-23 08:35 | 20-04-23 08:35 |  | Backout Closedown |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Stage | 170:(S3 VPN Big Pipe BO) | 11.0:(S3 VPN Big Pipe BO) | 1h 00m | - | 20-04-23 08:30 | 20-04-23 09:30 |  | Post Backout Tidy Up |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 171:(S3 VPN Big Pipe BO) | 11.1:(S3 VPN Big Pipe BO) | 1h 00m | - | 20-04-23 08:30 | 20-04-23 09:30 | EE Team | Close Dynamics TCR for Implementation |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 172:(S3 VPN Big Pipe BO) | 11.2:(S3 VPN Big Pipe BO) | 1h 00m | - | 20-04-23 08:30 | 20-04-23 09:30 | Implementation Manager | Gather Testing Results for Dynamics | Gather Testing evidence and attached to Change record |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Task | 173:(S3 VPN Big Pipe BO) | 11.3:(S3 VPN Big Pipe BO) | 1h 00m | - | 20-04-23 08:30 | 20-04-23 09:30 | Implementation Manager | Close MCR for Implementation | Answer following question in MCR: Attach Gathered Testing Evidence 17. Update this section with the relevant details pertaining to the issue which occurred during or post change. Below are the questions that need to be answered. 17a. What was the root cause of the issue? 17b. What was done to remediate the issue? 17c. What will be done to ensure this does not happen in the future again? |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046
Checkpoint | 174:(S3 VPN Big Pipe BO) | 11.4:(S3 VPN Big Pipe BO) | 0h 00m | - | 20-04-23 09:30 | 20-04-23 09:30 |  | Post Backout Tidy Up |  |  | N | None | None | None | None |  |  |  |  | S3 VPN Big Pipe BO | 466046

## Fancy Gantt (hidden)
Sun 16 Apr 2023
00:00
01:00
02:00
03:00
04:00
05:00
06:00
07:00
08:00
09:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
20:00
21:00
22:00
23:00
Mon 17 Apr 2023
00:00
01:00
02:00
03:00
04:00
05:00
06:00
07:00
08:00
09:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
20:00
21:00
22:00
23:00
Tue 18 Apr 2023
00:00
01:00
02:00
03:00
04:00
05:00
06:00
07:00
08:00
09:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
20:00
21:00
22:00
23:00
Wed 19 Apr 2023
00:00
01:00
02:00
03:00
04:00
05:00
06:00
07:00
08:00
09:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
20:00
21:00
22:00
23:00
Thu 20 Apr 2023
00:00
01:00
02:00
03:00
04:00
05:00
06:00
07:00
08:00
09:00
10:00
11:00
12:00
13:00
14:00
15:00
16:00
17:00
18:00
19:00
20:00
21:00
22:00
23:00
09:00
S3 VPN Connectivity Check
09:05
ON ICE Jobs - First Group
04:00
Deploy cmd Files - First Group
05:20
Enhanced Job Monitoring - First Group
12:00
Deploy cmd Files - Second Group
12:55
Enhanced Job Monitoring - Second Group
06:00
Enhanced Job Monitoring - Second Group
07:30
Deploy cmd Files - Third Group
09:05
Enhanced Job Monitoring - Third Group
08:00
Enhanced Job Monitoring - Third Group
466045
S3 VPN Big Pipe SoE
11:30
Prepare for Backout
12:00
Backout Dynamics cmd files Changes - First Group
12:30
Enhanced Job Monitoring - First Group
08:00
Backout Dynamics cmd files Changes - Second Group
12:55
Enhanced Job Monitoring - Second Group
06:00
Enhanced Job Monitoring - Second Group
08:00
Backout Dynamics cmd files Changes - Third Group
09:05
Enhanced Job Monitoring - Third Group
08:00
Enhanced Job Monitoring - Third Group
466046
S3 VPN Big Pipe BO
(Backout)

## Fancy Gantt Data (hidden)
STP Number | STP Name | Context | Phase | Stage | Stage Title | Start Time | End Time | Tech Detail | Shape-Exclude | Shape-Group | Shape-Name | Shape-Colour | Shape-Top
466045 | S3 VPN Big Pipe SoE | Imp | Pre
466045 | S3 VPN Big Pipe SoE | Imp | Pre | 1 | Pre-Implementation Access and Backup Activities
466045 | S3 VPN Big Pipe SoE | Imp | Imp
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 2 | Implementation Readiness |  |  | Shape:Exclude=Y | Y
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 3 | Readiness Check | 2023-04-16 09:00 | 2023-04-16 09:05 | Shape:Name=S3 VPN Connectivity Check Shape:Colour=205,225,243 |  |  | S3 VPN Connectivity Check | 205,225,243
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 4 | Milestone - Connectivity Confirmed |  |  | Shape:Exclude=Y | Y
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 4.1 | Internal Checkpoint - Connectivity Confirmed - Start Changes |  |  | Shape:Exclude=Y | Y
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 5 | ON ICE AutoSys Jobs before changes - Sunday | 2023-04-16 09:05 | 2023-04-16 09:15 | Shape:Name=ON ICE Jobs - First Group Shape:Colour=205,225,243 |  |  | ON ICE Jobs - First Group | 205,225,243
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 6 | cmd file Deployments - Monday 04:00 | 2023-04-17 04:00 | 2023-04-17 05:20 | Shape:Group=Group 1 Shape:Name= Deploy cmd Files - First Group Shape:Colour=205,225,243 |  | Group 1 | Deploy cmd Files - First Group | 205,225,243
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 7 | Adhoc Job runs to prove Autosys Setup | 2023-04-17 04:15 | 2023-04-17 05:00 | Shape:Group=Group 1 | Y | Group 1
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 8 | OFF ICE AutoSys Jobs after changes - Return to BAU | 2023-04-17 05:00 | 2023-04-17 05:20 | Shape:Group=Group 1 | Y | Group 1
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 9 | Milestone - Deployments Complete |  |  | Shape:Name=Milestone - Group 1 Deployments Complete Shape:Exclude=Y | Y |  | Milestone - Group 1 Deployments Complete
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 9.1 | Internal Checkpoint - All Code Deployments Complete |  |  | Shape:Exclude=Y | Y
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 10 | Monday Job Monitoring | 2023-04-17 05:20 | 2023-04-17 11:20 | Shape:Name=Enhanced Job Monitoring - First Group Shape:Colour=205,225,243 |  |  | Enhanced Job Monitoring - First Group | 205,225,243
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 11 | cmd file Deployments - Monday 12.00 | 2023-04-17 12:00 | 2023-04-17 13:00 | Shape:Group=Group2 Shape:Name=Deploy cmd Files - Second Group |  | Group2 | Deploy cmd Files - Second Group
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 12 | cmd file Deployments - Monday 12.00 | 2023-04-17 12:00 | 2023-04-17 12:10 | Shape:Group=Group2 | Y | Group2
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 13 | Monitoring - Group 2 Monday | 2023-04-17 12:55 | 2023-04-17 20:55 | Shape:Name=Enhanced Job Monitoring - Second Group |  |  | Enhanced Job Monitoring - Second Group
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 14 | Monitoring - Group 2 Tuesday | 2023-04-18 06:00 | 2023-04-18 10:00 | Shape:Name=Enhanced Job Monitoring - Second Group |  |  | Enhanced Job Monitoring - Second Group
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 15 | cmd file Deployments - Tuesday 07:30 | 2023-04-18 07:30 | 2023-04-18 07:40 | Shape:Name=Deploy cmd Files - Third Group Shape:Colour=48,84,150 |  |  | Deploy cmd Files - Third Group | 48,84,150
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 16 | Monitoring - Group 3 Tuesday | 2023-04-18 09:05 | 2023-04-18 17:30 | Shape:Name=Enhanced Job Monitoring - Third Group Shape:Colour=48,84,150 |  |  | Enhanced Job Monitoring - Third Group | 48,84,150
466045 | S3 VPN Big Pipe SoE | Imp | Imp | 17 | Monitoring - Group 3 Wednesday | 2023-04-19 08:00 | 2023-04-19 08:30 | Shape:Name=Enhanced Job Monitoring - Third Group Shape:Colour=48,84,150 |  |  | Enhanced Job Monitoring - Third Group | 48,84,150
466045 | S3 VPN Big Pipe SoE | Imp | Post
466045 | S3 VPN Big Pipe SoE | Imp | Post | 18 | Implementation Stand-down
466045 | S3 VPN Big Pipe SoE | Imp | Post | 18.1 | Milestone - Implementation Complete
466045 | S3 VPN Big Pipe SoE | Imp | Post | 19 | Post Implementation Tidy Up
466046 | S3 VPN Big Pipe BO | Bo | Imp
466046 | S3 VPN Big Pipe BO | Bo | Imp | 1 | Prepare for Backout | 2023-04-17 11:30 | 2023-04-17 12:30
466046 | S3 VPN Big Pipe BO | Bo | Imp | 1.1 | Internal Checkpoint - Start Backout of Changes |  |  | Shape:Exclude=Y | Y
466046 | S3 VPN Big Pipe BO | Bo | Imp | 2 | Backout Dynamics cmd files Changes - First Group | 2023-04-17 12:00 | 2023-04-17 12:35 | Shape:Colour=255,255,143 |  |  |  | 255,255,143
466046 | S3 VPN Big Pipe BO | Bo | Imp | 3 | Enhanced Job Monitoring - First Group | 2023-04-17 12:30 | 2023-04-17 16:30 | Shape:Colour=255,255,143 |  |  |  | 255,255,143
466046 | S3 VPN Big Pipe BO | Bo | Imp | 4 | Backout Dynamics cmd files Changes - Second Group | 2023-04-18 08:00 | 2023-04-18 08:35 | Shape:Colour=248,242,0 |  |  |  | 248,242,0
466046 | S3 VPN Big Pipe BO | Bo | Imp | 5 | Enhanced Job Monitoring - Second Group | 2023-04-18 12:55 | 2023-04-18 20:55 | Shape:Colour=248,242,0 |  |  |  | 248,242,0
466046 | S3 VPN Big Pipe BO | Bo | Imp | 6 | Enhanced Job Monitoring - Second Group | 2023-04-19 06:00 | 2023-04-19 10:00 | Shape:Colour=248,242,0 |  |  |  | 248,242,0
466046 | S3 VPN Big Pipe BO | Bo | Imp | 7 | Backout Dynamics cmd files Changes - Third Group | 2023-04-19 08:00 | 2023-04-19 08:35 | Shape:Colour=149,146,0 |  |  |  | 149,146,0
466046 | S3 VPN Big Pipe BO | Bo | Imp | 8 | Enhanced Job Monitoring - Third Group | 2023-04-19 09:05 | 2023-04-19 17:30 | Shape:Colour=149,146,0 |  |  |  | 149,146,0
466046 | S3 VPN Big Pipe BO | Bo | Imp | 9 | Enhanced Job Monitoring - Third Group | 2023-04-20 08:00 | 2023-04-20 08:30 | Shape:Colour=149,146,0 |  |  |  | 149,146,0
466046 | S3 VPN Big Pipe BO | Bo | Post
466046 | S3 VPN Big Pipe BO | Bo | Post | 10 | Backout Closedown
466046 | S3 VPN Big Pipe BO | Bo | Post | 10.1 | Internal Checkpoint - Backout of Changes Successfully Completed
466046 | S3 VPN Big Pipe BO | Bo | Post | 11 | Post Backout Tidy Up

## WS Sort (hidden)
Key | Type | Name | Sequence
1 | Info | Event Info | 0
2 | Sort | WS Sort | 1
1000 | BO | All Bo | 1000
100 | SoE | All Imp | 100